## Summary
Area | Defect Count
Saloon | 33
Aft Cockpit | 18
Fwd Cockpit Lounge & Deck | 10
Stbd Engine | 21
Port Engine | 23
Stbd Fwd Cabin & Heads | 34
Stbd Mid Cabin & Heads | 30
Stbd Aft Cabin & Heads | 38
Port Fwd Cabin & Heads | 33
Port Mid Cabin & Heads | 14
Port Aft Cabin & Heads | 34
Crew Cabin | 0

## Saloon
Defect Description | Discipline
Leak On Basin Plumbing | PLUM
Basin Mixer Loose | PLUM
Basin Cross Plumbed | PLUM
Junction Box Not Labeled | ELEC
Strip Lights Not Working | ELEC
Inverter Not Programmed On Acdc | ELEC
Inverter Alarm Not Working | ELEC
Watermaker Not Wired | ELEC
Loose Wires Behind Acdc | ELEC
Bilge Override Lights Not Working | ELEC
Filter Tap Fitted Wrong (Too Tight) | PLUM
Galley Fridge Not Working | ELEC
Genset Isolator Switch Not Mounted | CARP
2X Amplifiers Not Fitted | ELEC
Saloon Clear Plastic Db Cover Not Mounted | FA
Table Top Not Installed | CARP
Fire Blanket Not Fitted (Sf) | CARP
House Batteries Not Booted | ELEC
Mfd Not Showing Volts And Amps Of House Battery | ELEC
Co2 Sensor Not Mounted | CARP
Autopilot Cross Wired | ELEC
Galley Fridge Compressor Loosely Mounted | CARP
Saloon Tap Weight Mounted On Wrong Side Of Hose | PLUM
Telly Mute Not Working | ELEC
Nmma Label Needs To Be Mounted | FA
Aircon Switching On Wrong Pump | ELEC
Incomplete Wiring Behind Acdc Panel | ELEC
Incomplete Wiring At Main Saloon Db | ELEC
Aircon Not Working | ELEC
Saloon Door Needs To Be Set | CARP
Aircon Not Draining | PLUM
Incomplete Wiring On Db | ELEC
Speakers Not Working | ELEC

## Aft Cockpit
Defect Description | Discipline
Junction Box Not Labeled | ELEC
Strip Lights Not Working | ELEC
Mfd Not Showing Volts And Amps Of House Battery | ELEC
Autopilot Cross Wired | ELEC
Speakers Not Working | ELEC
Swim Ladder Bolts Loose | DECK
Davit Skew | DECK
Battery Link Not Working | ELEC
Vhf Wire Not Pulled Through | ELEC
Hin Number Incorrect | FA
Hin Number Sticker Not Fitted | FA
Shore Power Label Not Fitted | FA
R&C Decal Label / Dome Tag | FA
Jammer Labels Not Fitted | DECK
Raymic Fitting Upside Down | DECK
Engine Revs Do Not Align | MECH
No Teak Steps To Coach Roof Fitted | CARP
Mfd Needs To Be Updated | ELEC

## Fwd Cockpit Lounge & Deck
Defect Description | Discipline
Junction Box Not Labeled | ELEC
Strip Lights Not Working | ELEC
Speakers Not Working | ELEC
Touch Light Not Working | ELEC
Jammer Labels Not Fitted | DECK
Pulleys And Rope Painter Needs To Be Installed | DECK
Boom Labels Needs To Be Fitted | DECK
Oven Gas Shutoff Label Not Fitted | PLUM
Genset Breaker Not Labeled | ELEC
Gas Solenoid Not Wired | ELEC

## Stbd Engine
Defect Description | Discipline
Junction Box Not Labeled | ELEC
Ecu Not Labeled | ELEC
Topup Engine Fluids | MECH
Fuel Prefilter Pipe Clamps Loose | MECH
Expansion Tank Pipe Clamps Loose | MECH
Morse Control Splitpins Not Properly Bent Open | MECH
Loose L-Bracket On Starter Motor | MECH
Steering Cable Loose | MECH
Missing Labels At Filters Outboard | MECH
Missing Label On Battery | MECH
Touch Light Not Working | ELEC
Fuel Clamps Loose At Bulkhead | MECH
Engine Fuse Not Covered | ELEC
Battery Link Not Working | ELEC
Battery Cover Not Fitted | MECH
Loose Wire On Starter Solenoid | ELEC
Steering Bar Laying On Raw Fibre Glass | MECH
Alternator Negative Wire Not Connected | ELEC
Morse Control Cables Are Badly Routed | MECH
Engine Harness Not Strapped Up | ELEC
Engine Revs Do Not Align | MECH

## Port Engine
Defect Description | Discipline
Junction Box Not Labeled | ELEC
Ecu Not Labeled | ELEC
Topup Engine Fluids | MECH
Fuel Prefilter Pipe Clamps Loose | MECH
Expansion Tank Pipe Clamps Loose | MECH
Morse Control Splitpins Not Properly Bent Open | MECH
Loose L-Bracket On Starter Motor | MECH
Steering Cable Loose | MECH
Missing Labels At Filters Outboard | MECH
Missing Label On Battery | MECH
Touch Light Not Working | ELEC
Fuel Clamps Loose At Bulkhead | MECH
Engine Fuse Not Covered | ELEC
Battery Link Not Working | ELEC
Battery Cover Not Fitted | MECH
Loose Wire On Starter Solenoid | ELEC
Galvanic Isolator Wires Loose | ELEC
Steering Bar Laying On Raw Fibre Glass | MECH
Alternator Negative Wire Not Connected | ELEC
Morse Control Cables Are Badly Routed | MECH
Shore Power Breakers Not Labeled And No Rail Stopper | ELEC
Engine Harness Not Strapped Up | ELEC
Engine Revs Do Not Align | MECH

## Stbd Fwd Cabin & Heads
Defect Description | Discipline
Leak On Basin Plumbing | PLUM
Basin Mixer Loose | PLUM
Basin Cross Plumbed | PLUM
Junction Box Not Labeled | ELEC
Strip Lights Not Working | ELEC
Aircon Switching On Wrong Pump | ELEC
Aircon Not Working | ELEC
Aircon Not Draining | PLUM
Shower Mixer Loose | PLUM
Toilet Seat Loose | PLUM
Toilet Roll Holder Loose | CARP
Shower Sump Not Working | ELEC
Shower Rose Leaking | PLUM
Shower Mixer Leaking | PLUM
Waste Tank Leaking | PLUM
Leak On Toilet Plumbing | PLUM
Toilet Base Loose | PLUM
Aircon Pump Not Working | ELEC
Toilet Anti-Syphen Leaking | PLUM
Toilet Fresh Water Solenoid Not Working | ELEC
Waste Tank Indicator Not Working | ELEC
Cabin Fan Not Working | ELEC
Waste Tank Indicator Light Not Fitted | ELEC
Missing Salt/Fresh Label At Toilet | PLUM
Shower Leaking Into Bilge | PLUM
Toilet Salt/Fresh Is Cross Wired | ELEC
Shower Head Leaking | PLUM
Toilet Flush Defective | PLUM
Cabin Door Missing A Magnet Stopper | CARP
Toilet Flush Is Cross Wired | ELEC
Aircon Pump Pipes Leaking | PLUM
Aircon Connection Box Not Labeled | ELEC
Aircon Box Incorrectly Wired | ELEC
Missing Timmer Module For Aircon Relays | ELEC

## Stbd Mid Cabin & Heads
Defect Description | Discipline
Leak On Basin Plumbing | PLUM
Basin Mixer Loose | PLUM
Basin Cross Plumbed | PLUM
Junction Box Not Labeled | ELEC
Strip Lights Not Working | ELEC
Shower Mixer Loose | PLUM
Debree In Water Tank | PLUM
Toilet Seat Loose | PLUM
Water Tank Brace Loose | MECH
Toilet Roll Holder Loose | CARP
Shower Sump Not Working | ELEC
Shower Rose Leaking | PLUM
Shower Mixer Leaking | PLUM
Waste Tank Leaking | PLUM
Leak On Toilet Plumbing | PLUM
Toilet Base Loose | PLUM
High Level Float Not Working | ELEC
Low Level Float Not Working | ELEC
Toilet Anti-Syphen Leaking | PLUM
Toilet Fresh Water Solenoid Not Working | ELEC
Waste Tank Indicator Not Working | ELEC
Cabin Fan Not Working | ELEC
Waste Tank Indicator Light Not Fitted | ELEC
Missing Salt/Fresh Label At Toilet | PLUM
Shower Leaking Into Bilge | PLUM
Toilet Salt/Fresh Is Cross Wired | ELEC
Shower Head Leaking | PLUM
Toilet Flush Defective | PLUM
Cabin Door Missing A Magnet Stopper | CARP
Toilet Flush Is Cross Wired | ELEC

## Stbd Aft Cabin & Heads
Defect Description | Discipline
Leak On Basin Plumbing | PLUM
Basin Mixer Loose | PLUM
Basin Cross Plumbed | PLUM
Junction Box Not Labeled | ELEC
Strip Lights Not Working | ELEC
Aircon Switching On Wrong Pump | ELEC
Aircon Not Working | ELEC
Aircon Not Draining | PLUM
Incomplete Wiring On Db | ELEC
Shower Mixer Loose | PLUM
Debree In Water Tank | PLUM
Toilet Seat Loose | PLUM
Water Tank Brace Loose | MECH
Toilet Roll Holder Loose | CARP
Shower Sump Not Working | ELEC
Shower Rose Leaking | PLUM
Shower Mixer Leaking | PLUM
Waste Tank Leaking | PLUM
Leak On Toilet Plumbing | PLUM
Fuel Tank Brace Loose | MECH
Fuel Clamps Loose At Bulkhead | MECH
Toilet Base Loose | PLUM
High Level Float Not Working | ELEC
Low Level Float Not Working | ELEC
Toilet Anti-Syphen Leaking | PLUM
Toilet Fresh Water Solenoid Not Working | ELEC
Waste Tank Indicator Not Working | ELEC
Cabin Fan Not Working | ELEC
Waste Tank Indicator Light Not Fitted | ELEC
Missing Salt/Fresh Label At Toilet | PLUM
Shower Leaking Into Bilge | PLUM
Toilet Salt/Fresh Is Cross Wired | ELEC
Shower Head Leaking | PLUM
Toilet Flush Defective | PLUM
Cabin Door Missing A Magnet Stopper | CARP
Leak On Water Heater | PLUM
Toilet Flush Is Cross Wired | ELEC
Morse Control Cables Are Badly Routed | MECH

## Port Fwd Cabin & Heads
Defect Description | Discipline
Leak On Basin Plumbing | PLUM
Basin Mixer Loose | PLUM
Basin Cross Plumbed | PLUM
Junction Box Not Labeled | ELEC
Strip Lights Not Working | ELEC
Watermaker Not Wired | ELEC
Aircon Switching On Wrong Pump | ELEC
Aircon Not Working | ELEC
Aircon Not Draining | PLUM
Incomplete Wiring On Db | ELEC
Shower Mixer Loose | PLUM
Toilet Seat Loose | PLUM
Toilet Roll Holder Loose | CARP
Shower Sump Not Working | ELEC
Shower Rose Leaking | PLUM
Shower Mixer Leaking | PLUM
Touch Light Not Working | ELEC
Leak On Toilet Plumbing | PLUM
Toilet Base Loose | PLUM
Toilet Anti-Syphen Leaking | PLUM
Toilet Fresh Water Solenoid Not Working | ELEC
Waste Tank Indicator Not Working | ELEC
Cabin Fan Not Working | ELEC
Waste Tank Indicator Light Not Fitted | ELEC
Missing Salt/Fresh Label At Toilet | PLUM
Shower Leaking Into Bilge | PLUM
Toilet Salt/Fresh Is Cross Wired | ELEC
Shower Head Leaking | PLUM
Toilet Flush Defective | PLUM
Incorrect Wiring On Finder Relay For Genset | ELEC
Cabin Door Missing A Magnet Stopper | CARP
Toilet Flush Is Cross Wired | ELEC
Battery Cover Not Fitted | MECH

## Port Mid Cabin & Heads
Defect Description | Discipline
Junction Box Not Labeled | ELEC
Strip Lights Not Working | ELEC
Waste Tank Leaking | PLUM
High Level Float Not Working | ELEC
Low Level Float Not Working | ELEC
Aircon Pump Not Working | ELEC
Touchlight In High Voltage Locker Not Working | ELEC
Shower Leaking Into Bilge | PLUM
Aircon Pump Pipes Leaking | PLUM
Inverter Fans Not Working | ELEC
Inverter Touch Light Not Working | ELEC
Aircon Connection Box Not Labeled | ELEC
Aircon Box Incorrectly Wired | ELEC
Missing Timmer Module For Aircon Relays | ELEC

## Port Aft Cabin & Heads
Defect Description | Discipline
Leak On Basin Plumbing | PLUM
Basin Mixer Loose | PLUM
Basin Cross Plumbed | PLUM
Junction Box Not Labeled | ELEC
Strip Lights Not Working | ELEC
Aircon Switching On Wrong Pump | ELEC
Aircon Not Working | ELEC
Aircon Not Draining | PLUM
Incomplete Wiring On Db | ELEC
Shower Mixer Loose | PLUM
Debree In Water Tank | PLUM
Toilet Seat Loose | PLUM
Water Tank Brace Loose | MECH
Toilet Roll Holder Loose | CARP
Shower Sump Not Working | ELEC
Shower Rose Leaking | PLUM
Shower Mixer Leaking | PLUM
Leak On Toilet Plumbing | PLUM
Fuel Tank Brace Loose | MECH
Fuel Clamps Loose At Bulkhead | MECH
Toilet Base Loose | PLUM
Toilet Anti-Syphen Leaking | PLUM
Toilet Fresh Water Solenoid Not Working | ELEC
Waste Tank Indicator Not Working | ELEC
Cabin Fan Not Working | ELEC
Waste Tank Indicator Light Not Fitted | ELEC
Missing Salt/Fresh Label At Toilet | PLUM
Shower Leaking Into Bilge | PLUM
Toilet Salt/Fresh Is Cross Wired | ELEC
Shower Head Leaking | PLUM
Toilet Flush Defective | PLUM
Cabin Door Missing A Magnet Stopper | CARP
Leak On Water Heater | PLUM
Toilet Flush Is Cross Wired | ELEC

## Crew Cabin
Defect Description | Discipline