## C1019
PAGE 1 OF 5
[5 empty] | HULL NO: |  | C1019
CUST REF:
| RESPONSIBILITY: | [5 empty] | ARL. Van Veen
[14 empty] | Total | 91
COMMISSIONING DEFECTS Launch Date : | [8 empty] | TASK / JOB | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF | Elec | 45
|  | SALOON | [11 empty] | Plum | 25
| 1 | inverter alarm not working | [11 empty] | Mech | 6
| 2 | Autopilot motor Cross Wired | [11 empty] | Other | 15
| 3 | mast wiring incomplete
| 4 | deck light not working
| 5 | incorrectly labeled acdc panel
| 6 | missing deck wash label
| 7 | multimeters freezing and needs to be updated
| 8 | incorrect jump on shore 1 at acdc
| 9 | dual shore power breaker light is wired on wrong side
| 10 | TV lock pins incorrectly installed
| 11 | ACDC panel covers not fitted
| 12 | bilge alarm panel not mounted
| 13 | Incorrectly wired AC multimeter. Should measure genset and shore 1 not shore 2
| 14 | ACU ground wire not pulled through
| 15 | Telly Mute Not Working
| 16 | wireless charger not working
| 17 | missing negative bus bar cover
| 18 | lynxx2 cover loose
| 19 | saloon door not set
| 20 | AIS not working
| 21 | AIS not showing on MFD camera view
| 22 | Victron app setup not done
| 23 | Mfd Needs To Be Updated
| 24 | missing main breaker labels in saloon floor
| 25 | missing breaker labels on saloon DB
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs.
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | ARL. Van Veen |  | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | Page 2 of 5
[5 empty] | HULL NO: |  | C1019
CUST REF:
| RESPONSIBILITY: | [5 empty] | ARL. Van Veen
COMMISSIONING DEFECTS | [9 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
STBD AFT CABIN AND HEADS
| 26 | water pipe running over steering pulleys
| 27 | outboard AC outlet is upside down
| 28 | untidy morse control cables inboard
| 29 | shower hot water kinked
| 30 | toilet pipes not cradled
| 31 | wires covering toilet anti-syphen
| 32 | aircon drain too long
| 33 | water heater drain not cradled
| 34 | Toilet Seat Loose
| 35 | Toilet Base Loose
| 36 | Basin Mixer Loose
| 37 | leak on waste tank
STBD FWD CABIN AND HEADS
| 38 | CO sensor not working
| 39 | bad duckting inboard
| 40 | depth transducer wire not cradled
| 41 | Shower Leaking Into Bilge
| 42 | basin not properly draining (water collects in corner)
| 43 | depth transducer label missing
| 44 | Toilet Seat Loose
| 45 | Toilet Base Loose
| 46 | basin mixer loose
| 47 | loose pipes in bilge
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | ARL. Van Veen |  | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | PAGE 3 OF 5
[5 empty] | HULL NO: |  | C1019
CUST REF:
| RESPONSIBILITY: | [5 empty] | ARL. Van Veen
COMMISSIONING DEFECTS | [9 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
PORT FWD CABIN & Heads
| 48 | wireless charger wire not strapped
| 49 | speed transducer wire not cradled
| 50 | speed transducer missing label
PORT AFT CABIN & Heads
| 51 | duckting not neat
| 52 | isolator switch mounted skew
| 53 | remove plastic in inverter fans
| 54 | aircon drain too long
| 55 | water heater drain too long
| 56 | water tank dirty
PORT PASSAGE
| 57 | label breakers in HVL
| 58 | loose pipes in bilge
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | ARL. Van Veen |  | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | PAGE 4 OF 5
[5 empty] | HULL NO: |  | C1019
CUST REF:
| RESPONSIBILITY: | [5 empty] | ARL. Van Veen
COMMISSIONING DEFECTS | [9 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
AFT COCKPIT
| 59 | steering is stiff and clicking
| 60 | davit is skew
| 61 | camera skew
| 62 | incorrect label on liferaft locker
| 63 | Raymic Fitting Upside Down
| 64 | fuel transfer is not working
| 65 | helm cup holders not draining
| 66 | compass light not working
| 67 | incorrect steering wheel fitted
PORT ENGINE ROOM
| 68 | emergency tiller getting stuck
| 69 | bad ground wire crimp on rudder
| 70 | bad heat shrink on gnd bus bar
| 71 | Ecu Not Labeled
| 72 | coolant under engine
| 73 | stern shower mixer skew
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs.
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | ARL. Van Veen |  | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | PAGE 5 OF 5
[5 empty] | HULL NO: |  | C1019
CUST REF:
| RESPONSIBILITY: | [5 empty] | ARL. Van Veen
COMMISSIONING DEFECTS | [9 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
STB ENGINE ROOM
| 74 | emergency tiller getting stuck
| 75 | shore power box missing blanks
| 76 | Ecu Not Labeled
| 77 | unwanted shore power jump wire
| 78 | float switch not properly functioning
| 79 | shore power breakers not labeled
| 80 | galvanic isolator cables loose
| 81 | rust and dirt on engine
FWD COCKPIT, SIDE DECKS AND COACH ROOF
| 82 | camera is skew
| 83 | windlass brake is too tight
| 84 | missing boots on windlass motor
| 85 | windlass junction box loosely mounted
| 86 | incorrect washdown fitting (should be black)
| 87 | fwd cockpit fusion remote not picking up network
EXTRAS
| 88 | all outlets to be tested
| 89 | All bilge labels to be checked
| 90 | Fresh/Salt water labels for toilets to be fitted
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs.
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | ARL. Van Veen |  | SIGNATURE:

## C1018
PAGE 1 OF 5
[5 empty] | HULL NO: |  | C1018
CUST REF:
| RESPONSIBILITY: | [5 empty] | ARL. Van Veen
[14 empty] | Total | 106
COMMISSIONING DEFECTS Launch Date : | [8 empty] | TASK / JOB | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF | Elec | 0
|  | SALOON | [11 empty] | Plum | 0
| 1 | saloon fridge not cooling | [11 empty] | Mech | 0
| 2 | Nmma Label Needs To Be Mounted | [11 empty] | Other | 106
| 3 | genset volts and hertz not correctly set
| 4 | genset transfer breaker light not going on
| 5 | mast wiring needs to be done
| 6 | Saloon Door Needs To Be Set
| 7 | missing clamp for fridge drain pipe
| 8 | Oven cluster not working
| 9 | bilge alarm panel not mounted
| 10 | Saloon Clear Plastic Db Cover Not Mounted
| 11 | Fire Blanket Not Fitted (Sf)
| 12 | Co2 Sensor Not Mounted
| 13 | incorrect acdc panel labels
| 14 | incorrect colour code wire under helm on bus bar
| 15 | missing labels for main breakers in floor
| 16 | Autopilot RF remote not connected
| 17 | no Co-X plugs fitted for VHF antenna
| 18 | MFD needs to be updated
| 19 | AC Multimeter needs to be programmed
| 20 | No key tallies for saloon door fitted
| 21 | missing bus bar cover in saloon floor
| 22 | lynxx 2 cover loose
| 23 | battery brace loose
| 24 | saloon tap weight badly installed
| 25 | aircon pump not switching on
| 26 | morse control idle revs misaligned
| 27 | shore power 1 not working (incorrectly wired)
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs.
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | ARL. Van Veen |  | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | Page 2 of 5
[5 empty] | HULL NO: |  | C1018
CUST REF:
| RESPONSIBILITY: | [5 empty] | ARL. Van Veen
COMMISSIONING DEFECTS | [9 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
STBD AFT CABIN AND HEADS
| 28 | fuel pipes metal support frame loose
| 29 | water heater drain pipe not cradled
| 30 | helm cup holder drain not correctly installed
| 31 | Basin Mixer Loose
| 32 | Shower Mixer Loose
| 33 | Toilet Seat Loose
| 34 | Toilet Base Loose
| 35 | manual fire suppression cable loose
| 36 | Aircon Not Draining
| 37 | aircon pump not switching on
| 38 | helm cup holder drain badly installed
| 39 | fridge compressor not mounted
| 40 | OV cabin door lock incorrectly installed
| 41 | Toilet Salt/Fresh Is Cross Wired
| 42 | toilet solenoid broke loose
STBD FWD CABIN AND HEADS
| 43 | Toilet Salt/Fresh Is Cross Wired
| 44 | outlet upside down
| 45 | aircon box cover not fitted
| 46 | missing ball valve label
| 47 | Shower Mixer Loose
| 48 | Toilet Seat Loose
| 49 | Toilet Base Loose
| 50 | Basin Mixer Loose
| 51 | missing j-box cover in bilge
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | ARL. Van Veen |  | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | PAGE 3 OF 5
[5 empty] | HULL NO: |  | C1018
CUST REF:
| RESPONSIBILITY: | [5 empty] | ARL. Van Veen
COMMISSIONING DEFECTS | [9 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
PORT FWD CABIN & Heads
| 52 | Toilet Seat Loose
| 53 | Toilet Base Loose
| 54 | Basin Mixer Loose
| 55 | aircon pump not switching on
| 56 | excess gas piping behind genset battery inboard
| 57 | Toilet Salt/Fresh Is Cross Wired
PORT AFT CABIN & Heads
| 58 | aircon pump not switching on
| 59 | Toilet Seat Loose
| 60 | Toilet Base Loose
| 61 | Basin Mixer Loose
| 62 | unlabeled wires and busbar at yachtsense
| 63 | water heater drain pipe not cradled
| 64 | aircon drain pipe too long
| 65 | loose connections on yachtsense
| 66 | missing c-clips at aircon bleed
| 67 | AIS not wired
| 68 | manual fire suppression cable loose
PORT PASSAGE
| 69 | loose toilet piping
| 70 | missing breaker labels
| 71 | missing j-box cover in bilge
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | ARL. Van Veen |  | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | PAGE 4 OF 5
[5 empty] | HULL NO: |  | C1018
CUST REF:
| RESPONSIBILITY: | [5 empty] | ARL. Van Veen
COMMISSIONING DEFECTS | [9 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
AFT COCKPIT
| 72 | underwater lights not working
| 73 | badly installed shore power socket screws both port and stbd side
| 74 | dome tag not fitted
| 75 | transom teak steps SF
| 76 | saloon door missing cover plate on port side
| 77 | saloon door missing interior valence
| 78 | aft cockpit strip light not connected
| 79 | genset battery voltage is showing on mfd if isolator is off
PORT ENGINE ROOM
| 80 | Ecu Not Labeled
| 81 | Missing Label On Battery
| 82 | rust on engine
| 83 | loose exhaust clamp
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs.
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | ARL. Van Veen |  | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | PAGE 5 OF 5
[5 empty] | HULL NO: |  | C1018
CUST REF:
| RESPONSIBILITY: | [5 empty] | ARL. Van Veen
COMMISSIONING DEFECTS | [9 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
STB ENGINE ROOM
| 84 | Ecu Not Labeled
| 85 | Missing Label On Battery
| 86 | autopilot overturns and gets stuck
| 87 | badly installed engine ground wire
| 88 | shore power breakers not labeled
| 89 | remove unwanted boot on battery
| 90 | extra jump in shore power contactor box (unwanted)
| 91 | loose exhaust clamp
FWD COCKPIT, SIDE DECKS AND COACH ROOF
| 92 | windlass is slipping
| 93 | deckwash is leaking
| 94 | windlass boot missing
| 95 | genset breaker not labeled
| 96 | windlass chain teflon block badly installed (remove teflon block or fix mounting)
| 97 | stbd deck winch not working
| 98 | mainsheet deck winch button needs to be removed. It is not a electric winch
| 99 | missing label in gas locker shutoff valve
| 100 | raymic outlet is skew
| 101 | Jammer Labels Not Fitted
| 102 | deck winches silver tops do not align
| 103 | boom warning labels to be fitted
EXTRAS
| 104 | toilet salt/fresh labels
| 105 | mount fire extinguishers
| 106 | electrical labeling needs to be done
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs.
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | ARL. Van Veen |  | SIGNATURE:

## C1013
PAGE 1 OF 5
[5 empty] | HULL NO: |  | C1013
CUST REF:
| RESPONSIBILITY: | [5 empty] | ARL. Van Veen
[14 empty] | Total | 123
COMMISSIONING DEFECTS Launch Date : | [8 empty] | TASK / JOB | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF | Elec | 64
|  | SALOON | [11 empty] | Plum | 37
| 1 | buzzer not connected by helm | [11 empty] | Mech | 13
| 2 | Nmma Label Needs To Be Mounted | [11 empty] | Other | 9
| 3 | genset volts and hertz not correctly set
| 4 | incomplete wiring by main DB
| 5 | mast wiring needs to be done
| 6 | Saloon Door Needs To Be Set
| 7 | missing clamp for fridge drain pipe
| 8 | missing diodes by main DB
| 9 | stbd fwd shower pump wire needs to be strapped to main db
| 10 | Saloon Clear Plastic Db Cover Not Mounted
| 11 | Fire Blanket Not Fitted (Sf)
| 12 | Co2 Sensor Not Mounted
| 13 | incorrect acdc panel labels
| 14 | curtacy lights incorrectly wired
| 15 | missing labels for main breakers in floor
| 16 | inverter network cable pulled out
| 17 | no Co-X plugs fitted for VHF antenna
| 18 | MFD needs to be updated
| 19 | AC Multimeter needs to be programmed
| 20 | No key tallies for saloon door fitted
| 21 | Autopilot motor not working
| 22 | DC multimeter freezing
| 23 | incorrectly wired AC neutrals
| 24 | DC multimeter arrow cross wired
| 25 | deck light not working
| 26 | AC cluster incorrectly wired
| 27 | shore power 2 not working (incorrectly wired)
| 28 | VHF antenna wire not pulled through from nav station
| 29 | Galley Fridge Not Working
| 30 | watermaker polarity incorrect
| 31 | telly mute not working
| 32 | bilge notification popups not working
| 33 | inverter alarm incorrectly wired
| 34 | bilge helm light not working
| 35 | windlass only works with port ignition
| 36 | Victron app on MFD not configured
| 37 | port water heater not working
| 38 | stereo keeps tripping
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs.
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | ARL. Van Veen |  | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | Page 2 of 5
[5 empty] | HULL NO: |  | C1013
CUST REF:
| RESPONSIBILITY: | [5 empty] | ARL. Van Veen
COMMISSIONING DEFECTS | [9 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
STBD AFT CABIN AND HEADS
| 39 | water heater leaking at hot water
| 40 | water heater drain pipe not cradled
| 41 | helm cup holder drain not correctly installed
| 42 | Basin Mixer Loose
| 43 | Shower Mixer Loose
| 44 | Toilet Seat Loose
| 45 | Toilet Base Loose
| 46 | wires needs to be strapped in inboard inspection
| 47 | ACU ground wire not connected
| 48 | co2 sensor not working
STBD MID CABIN AND HEADS
| 49 | Toilet Seat Loose
| 50 | Toilet Base Loose
| 51 | inboard piping not cradled
| 50 | 2way switch fitted -- should be three way
| 51 | ventilation fan not fitted
STBD FWD CABIN AND HEADS
| 52 | aircon elbow broken
| 53 | poor aircon duckting
| 54 | loose pipes by aircon
| 55 | missing ball valve label
| 56 | Shower Mixer Loose
| 57 | Toilet Seat Loose
| 58 | Toilet Base Loose
| 59 | Basin Mixer Loose
| 60 | aircon base loose
| 61 | toilet switch not wired
| 62 | outlet not wired
| 63 | aircon not working
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | ARL. Van Veen |  | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | PAGE 3 OF 5
[5 empty] | HULL NO: |  | C1013
CUST REF:
| RESPONSIBILITY: | [5 empty] | ARL. Van Veen
COMMISSIONING DEFECTS | [9 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
PORT FWD CABIN & Heads
| 64 | Toilet Seat Loose
| 65 | Toilet Base Loose
| 66 | Basin Mixer Loose
| 67 | badly installed duckting
| 68 | watermaker prefilter is damaged
PORT AFT CABIN & Heads
| 69 | Waste Tank Indicator Not Working
| 70 | Toilet Seat Loose
| 71 | Toilet Base Loose
| 72 | Basin Mixer Loose
| 73 | aircon duckting loose
| 74 | water heater drain pipe not cradled
| 75 | aircon drain pipe too long
| 76 | loose connections on yachtsense
PORT PASSAGE
| 77 | loose toilet piping
| 78 | aircon pump pipe too long
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | ARL. Van Veen |  | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | PAGE 4 OF 5
[5 empty] | HULL NO: |  | C1013
CUST REF:
| RESPONSIBILITY: | [5 empty] | ARL. Van Veen
COMMISSIONING DEFECTS | [9 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
AFT COCKPIT
| 78 | stern shower mixer upside down
| 78 | stern shower nozzle leaking
| 78 | dome tag not fitted
| 78 | Davit Skew
| 78 | usb fitted at incorrect location
| 78 | davit switch badly mounted
| 78 | shore power grommets badly fitted
| 78 | shore power plugs not fitted
| 78 | stbd mid extractor mushroom not fitted
| 78 | genset battery voltage is showing on mfd if isolator is off
| 78 | fusion remote not picking up
| 78 | fireboy display defective
PORT ENGINE ROOM
| 79 | Ecu Not Labeled
| 80 | Missing Label On Battery
| 81 | Loose L-Bracket On Starter Motor
| 82 | cyrix status led not flashing
| 83 | engine raw water pipe is dirty
| 84 | stern shower pipe is kinked
| 85 | Fuel Prefilter Pipe Clamps Loose
| 86 | single clamps on fuel and coolant pipe
| 87 | no fireboy terminator plug
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs.
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | ARL. Van Veen |  | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | PAGE 5 OF 5
[5 empty] | HULL NO: |  | C1013
CUST REF:
| RESPONSIBILITY: | [5 empty] | ARL. Van Veen
COMMISSIONING DEFECTS | [9 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
STB ENGINE ROOM
| 88 | Ecu Not Labeled
| 89 | Missing Label On Battery
| 90 | bilge float chaffing (getting stuck)
| 91 | badly installed engine ground wire
| 92 | shore power breakers not labeled
| 93 | blue steering conduit at an angle
| 94 | Fuel Prefilter Pipe Clamps Loose
| 95 | single clamps on fuel and coolant pipe
| 96 | no fireboy terminator plug
| 97 | FWD COCKPIT, SIDE DECKS AND COACH ROOF
| 98 | windlass cables on wrong side of bulkhead
| 99 | genset cap leaking coolant
| 100 | windlass boots missing
| 101 | genset breaker not labeled
| 102 | windlass base is loose
| 103 | genset leak alarm not working
| 104 | incorrectly wired genset earth leakage
| 105 | water level not showing on MFD
| 106 | auto pilot motor not wired
| 107 | throttle rpms not aligning
| 108 | steering is clicking
| 109 | boom warning labels to be fitted
| 110 | damage on boom
| 111 | Jammer Labels Not Fitted
| 112 | Pulleys And Rope Painter Needs To Be Installed
| 113 | fusion remote and speaker not working on flybridge
| 114 | fwd camera is skew
| 115 | deck winches silver tops do not align
| 116 | victron app setup to be done
| 117 | port water tank sensor defective
| 118 | deck light not working
EXTRAS
| 119 | aircon programming
| 120 | hull decals
| 121 | toilet salt/fresh labels
| 122 | mount fire extinguishers
| 123 | electrical labeling needs to be done
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs.
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | ARL. Van Veen |  | SIGNATURE:

## C1017
PAGE 1 OF 5
[5 empty] | HULL NO: |  | C1017
CUST REF:
| RESPONSIBILITY: | [5 empty] | ARL. Van Veen
[14 empty] | Total | 132
COMMISSIONING DEFECTS Launch Date : | [8 empty] | TASK / JOB | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF | Elec | 62
|  | SALOON | [11 empty] | Plum | 37
| 1 | incorrect wires (colour codes) used for light switches (multiple) | [11 empty] | Mech | 14
| 2 | Nmma Label Needs To Be Mounted | [11 empty] | Other | 19
| 3 | genset volts and hertz not correctly set
| 4 | 2x missing downlights
| 5 | mast wiring needs to be done
| 6 | Saloon Door Needs To Be Set
| 7 | missing clamp for fridge drain pipe
| 8 | saloon settee armrest bolts cut off too short
| 9 | lifting platform isolator not mounted
| 10 | Saloon Clear Plastic Db Cover Not Mounted
| 11 | Fire Blanket Not Fitted (Sf)
| 12 | Co2 Sensor Not Mounted
| 13 | incorrect acdc panel labels
| 14 | genset transfer causing finder behind ACDC to gitter
| 15 | missing labels for main breakers in floor
| 16 | 2x unused loose wires behind ACDC
| 17 | no Co-X plugs fitted for VHF antenna
| 18 | MFD needs to be updated
| 19 | AC Multimeter needs to be programmed
| 20 | No key tallies for saloon door fitted
| 21 | Autopilot motor cross wired
| 22 | DC multimeter freezing
| 23 | Bad crimp on battery protect unit
| 24 | house battery cables not properly routed and strapped
| 25 | deck light not working
| 26 | curtacy lights incorrectly wired
| 27 | stbd engine battery voltage not showing on dc meter
| 28 | VHF antenna wire not pulled through from nav station
| 29 | horn button not working
| 30 | Shore 2 not working (incorrect contactor wiring)
| 31 | telly mute not working
| 32 | induction HOB not working
| 33 | inverter alarm incorrectly wired
| 34 | Main saloon breakers not mounted
| 35 | Inverter incorrectly programmed
| 36 | Victron app on MFD not configured
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs.
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | ARL. Van Veen |  | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | Page 2 of 5
[5 empty] | HULL NO: |  | C1017
CUST REF:
| RESPONSIBILITY: | [5 empty] | ARL. Van Veen
COMMISSIONING DEFECTS | [9 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
STBD AFT CABIN AND HEADS
| 37 | toilet salt water not working
| 38 | toilet fresh water not working
| 39 | Toilet Seat Loose
| 40 | toilet loose
| 41 | inboard inspection pipes not strapped
| 42 | float switch chemical damage
| 43 | badly installed duckting
| 44 | aircon drain pipe too long
| 45 | water heater drain pipe not cradled
| 46 | toilet plumbing leaking
| 47 | 2x cut AC wires because stuck in steering
| 48 | helm cup holder's not properly draining
| 49 | bad morse control cable installation
| 50 | no plugs fitted for aircon unit
STBD MID CABIN AND HEADS
N/A
STBD FWD CABIN AND HEADS
| 51 | duckting badly installed
| 52 | missing rail stoppers for finder
| 53 | extra unused relay on DB
| 54 | shower inspection leaking
| 55 | Basin Mixer Loose
| 56 | Shower Mixer Loose
| 57 | Toilet Seat Loose
| 58 | waste tank strap badly installed
| 59 | Waste Tank Indicator Light Not working
| 60 | aircon filter leaking
| 61 | aircon t-piece leaking
| 62 | aircon blead leaking
| 63 | depth transducer dummy not fitted
| 64 | Missing Salt/Fresh Label At Toilet
| 65 | water purifier mounted at different location
| 66 | incorrect aircon pump wiring
| 67 | missing deckwask through hull label
| 68 | cabin light wires badly installed
| 69 | basin water gathering in corner and needs to be filled up
| 70 | no plugs fitted for aircon unit
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | ARL. Van Veen |  | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | PAGE 3 OF 5
[5 empty] | HULL NO: |  | C1017
CUST REF:
| RESPONSIBILITY: | [5 empty] | ARL. Van Veen
COMMISSIONING DEFECTS | [9 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
PORT FWD CABIN & Heads
| 71 | speed transducer wire not cradled
| 72 | Basin Mixer Loose
| 73 | toilet loose
| 74 | Toilet Seat Loose
| 75 | Missing Salt/Fresh Label At Toilet
PORT AFT CABIN & Heads
| 76 | aircon drain pipe too long
| 77 | water heater overflow pipe not cradled
| 78 | Basin Mixer Loose
| 79 | Toilet Seat Loose
| 80 | toilet loose
| 81 | toilet anti-syten leaking
| 82 | aircon pump leaking
| 83 | toilet pump leaking
| 84 | water heater wires not strapped
| 85 | isolator switch wires not strapped
| 86 | untidy wiring in inboard inspection
| 87 | badly layed genset exhaust pipe
| 88 | bad wire routing under yachtsense
| 89 | aircon pump wiring incorrect
PORT PASSAGE
| 90 | aircon filter leaking
| 91 | outboard piping not strapped
| 92 | unused watermaker wires under inverter (wastage)
| 93 | HVL busbar cover not fitted
| 94 | missing breaker labels and blanks
| 95 | missing blank in solar box
| 96 | missing ground on earth bonding plate
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | ARL. Van Veen |  | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | PAGE 4 OF 5
[5 empty] | HULL NO: |  | C1017
CUST REF:
| RESPONSIBILITY: | [5 empty] | ARL. Van Veen
COMMISSIONING DEFECTS | [9 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
AFT COCKPIT
| 96 | lifting platform mechanical stop needs to be adjusted
| 96 | fridge not mounted
| 96 | Raymic Fitting Upside Down
| 96 | fuel transfer is not working
PORT ENGINE ROOM
| 97 | loose cradle of rudder post ground wire
| 98 | single clamps on fuel lines
| 99 | single clamps on coolant lines
| 100 | dirt/rust under engine
| 101 | emergensy tiller not engaging
| 102 | battery label not fitted
| 103 | battery positive terminal loose
| 104 | loose pipe on stern shower mixer
| 105 | stern shower mixer skew
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs.
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | ARL. Van Veen |  | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | PAGE 5 OF 5
[5 empty] | HULL NO: |  | C1017
CUST REF:
| RESPONSIBILITY: | [5 empty] | ARL. Van Veen
COMMISSIONING DEFECTS | [9 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
STB ENGINE ROOM
| 106 | shore power ground bus cover not fitted
| 107 | bad crimp on rudder gnd wire
| 108 | incorrect colour blanks in hager box
| 109 | steering cable in blue sleeve is at an angle
| 110 | loose wires on galvanic isolator
| 111 | poor heat shrink on galvanic isolator
| 112 | engine anti-syfen leaking
| 113 | coolant of engine was badly topped up
| 114 | emergency tiller not engaging
| 115 | single clamps on fuel lines
| 116 | single clamps on coolant lines
| 117 | Ecu Not Labeled
| 118 | Missing Label On Battery
| 119 | missing blower pipe
FWD COCKPIT, SIDE DECKS AND COACH ROOF
| 120 | standing rigging is too long
| 121 | missing boots on windlass control box and motor
| 122 | missing screws for genset cover
| 123 | genset ground leakage incorrectly installed
| 124 | fwd cockpit stbd strip light defective
| 125 | fwd cockpit fusion defective
| 126 | deckwash pump not working
| 127 | No voltage pushing through genset earth leakage (how was AC declared working?)
EXTRAS
| 128 | aircon programming
| 129 | hull decals
| 130 | guard rails hitting stanctions
| 131 | mount fire extinguishers
| 132 | electrical labeling needs to be done
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs.
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | ARL. Van Veen |  | SIGNATURE:

## C1015
PAGE 1 OF 5
[5 empty] | HULL NO: |  | C1015
CUST REF:
| RESPONSIBILITY: | [5 empty] | ARL. Van Veen
[14 empty] | Total | 121
COMMISSIONING DEFECTS Launch Date : | [8 empty] | TASK / JOB | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF | Elec | 34
|  | SALOON | [11 empty] | Plum | 41
| 1 | ACDC covers not fitted | [11 empty] | Mech | 27
| 2 | Nmma Label Needs To Be Mounted | [11 empty] | Other | 19
| 3 | genset volts and hertz not correctly set
| 4 | windlass not working on stbd ignition
| 5 | mast wiring needs to be done
| 6 | Saloon Door Needs To Be Set
| 7 | missing clamp for fridge drain pipe
| 8 | Telly Mute Not Working
| 9 | compass light not working
| 10 | Saloon Clear Plastic Db Cover Not Mounted
| 11 | Fire Blanket Not Fitted (Sf)
| 12 | Co2 Sensor Not Mounted
| 13 | incorrect acdc panel labels
| 14 | reefing warning sign not fitted in galley
| 15 | missing labels for main breakers in floor
| 16 | house batteries brace loose
| 17 | no Co-X plugs fitted for VHF antenna
| 18 | MFD needs to be updated
| 19 | AC Multimeter needs to be programmed
| 20 | No key tallies for saloon door fitted
| 21 | Autopilot motor not connected
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs.
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | ARL. Van Veen |  | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | Page 2 of 5
[5 empty] | HULL NO: |  | C1015
CUST REF:
| RESPONSIBILITY: | [5 empty] | ARL. Van Veen
COMMISSIONING DEFECTS | [9 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
STBD AFT CABIN AND HEADS
| 22 | Leak On Water Heater
| 23 | unused cradle in fuel locker
| 24 | loose fire suppression cable
| 25 | helm cup holders do not drain into aircon drain
| 26 | heads floor leaking into bilge
| 27 | Toilet Salt/Fresh Is Cross Wired
| 28 | Missing Salt/Fresh Label At Toilet
| 29 | Toilet Seat Loose
| 30 | Basin Mixer Loose
| 31 | ducting is badly installed in ceiling
| 32 | toilet pipe leaking
| 33 | badly installed morse control cables in ceiling below helm
| 34 | badly strapped wiring in ceiling below helm
STBD MID CABIN AND HEADS
| 35 | extractor fan pipe not connected to deck mushroom
| 36 | extractor fan fitted skew
| 37 | Toilet Base Loose
| 38 | Toilet Anti-Syphen Leaking
| 39 | toilet salt water is blocked
| 40 | heads rope light not working
| 41 | Toilet Salt/Fresh Is Cross Wired
| 42 | inboard inspection has a pipe that is not draining properly
| 43 | unused cradels and plumbing not cradled inboard inspection
| 44 | Water Tank Brace Loose
STBD FWD CABIN AND HEADS
| 45 | missing blue clip for aircon finder relay
| 46 | Toilet Salt/Fresh Is Cross Wired
| 47 | extra aircon bleed label fitted
| 48 | depth transducer dummy plug not on boat (used for C1012)
| 49 | Toilet Seat Loose
| 50 | Basin Mixer Loose
| 51 | Toilet Base Loose
| 52 | Missing Salt/Fresh Label At Toilet
| 53 | Shower Leaking Into Bilge
| 54 | leak on aircon pump
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | ARL. Van Veen |  | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | PAGE 3 OF 5
[5 empty] | HULL NO: |  | C1015
CUST REF:
| RESPONSIBILITY: | [5 empty] | ARL. Van Veen
COMMISSIONING DEFECTS | [9 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
PORT FWD CABIN & Heads
| 55 | watermaker requires commissioning
| 56 | toilet pump leaking
| 57 | shower leaking into bilge
| 58 | bad duckting of aircon
| 59 | genset battery base installed at incorrect location
| 60 | Toilet Seat Loose
| 61 | Basin Mixer Loose
| 62 | Toilet Salt/Fresh Is Cross Wired
| 63 | Missing Salt/Fresh Label At Toilet
| 64 | Toilet Base Loose
PORT AFT CABIN & Heads
| 65 | Shower Mixer Loose
| 66 | Toilet Salt/Fresh Is Cross Wired
| 67 | aircon filter leaking
| 68 | aircon pump leaking
| 69 | Water Tank Brace Loose
| 70 | Aircon Not Draining
| 71 | Missing Salt/Fresh Label At Toilet
| 72 | Toilet Seat Loose
| 73 | Basin Mixer Loose
| 74 | toilet pump leaking
| 75 | Toilet Base Loose
PORT PASSAGE
| 76 | toilet ballvalve broken
| 77 | missing aircon bleed label
| 78 | aircon filter leaking
| 79 | toilet pump leaking
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | ARL. Van Veen |  | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | PAGE 4 OF 5
[5 empty] | HULL NO: |  | C1015
CUST REF:
| RESPONSIBILITY: | [5 empty] | ARL. Van Veen
COMMISSIONING DEFECTS | [9 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
AFT COCKPIT
| 79 | Davit Skew
| 79 | 12V helm outlet location to be determined
| 79 | davit motor not booted
| 79 | davit contactor not booted
| 79 | Davit contactor loose
| 79 | raymic wire is not mounted
| 79 | Battery Link Not Working (wire not pulled through)
| 79 | transom teak steps needs to be fitted
| 79 | liferaft locker backrest supports needs to be fitted
PORT ENGINE ROOM
| 80 | Topup Engine Fluids
| 81 | engine battery not labeled
| 82 | Morse Control Splitpins Not Properly Bent Open
| 83 | single clamps on fuel prefilter
| 84 | fireboy harness terminator plugs not fitted (SF)
| 85 | stern shower tap mounted skew, leaking and wire pipe kinked
| 86 | loose morse control nut
| 87 | single clamps on coolant piping to waterheater
| 88 | Ecu Not Labeled
| 89 | Steering Cable Loose
| 90 | no teflon strips for steering bar
| 91 | exhaust temp sensor loose
| 92 | multiple loose pipes and single clamps
| 93 | underwater light gnd wire loose
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs.
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | ARL. Van Veen |  | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | PAGE 5 OF 5
[5 empty] | HULL NO: |  | C1015
CUST REF:
| RESPONSIBILITY: | [5 empty] | ARL. Van Veen
COMMISSIONING DEFECTS | [9 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
STB ENGINE ROOM
| 94 | loose underwater light nut
| 95 | bilge pump used for C1012
| 96 | fireboy harness terminator plugs not fitted (SF)
| 97 | Morse Control Splitpins Not Properly Bent Open
| 98 | single clamps on fuel prefilter
| 99 | exhaust temp sensor loose
| 100 | Ecu Not Labeled
| 101 | saildrive oil low
| 102 | prefilter and pipes loose
| 103 | earth wire of underwater light loose
| 104 | poorly fitted clamps on raw water pipes
| 105 | missing clamp covers
| 106 | unused craddle by breath pipe
FWD COCKPIT, SIDE DECKS AND COACH ROOF
| 107 | AR200 cover broken
| 108 | spray dodger needs to be fitted
| 109 | defective 72mm block for main sheet
| 110 | genset coolant cap leaking
| 111 | Boom Labels Needs To Be Fitted
| 112 | Jammer Labels Not Fitted
| 113 | steering has a sound
| 114 | missing boots on windlass motor and control box
| 115 | missing windlass junction box
| 116 | missing gas locker label
EXTRAS
| 117 | aircon programming
| 118 | hull decals
| 119 | guard rails hitting stanctions
| 120 | mount fire extinguishers
| 121 | electrical labeling needs to be done
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs.
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | ARL. Van Veen |  | SIGNATURE:

## C1012
PAGE 1 OF 5
[5 empty] | HULL NO: |  | C1012
CUST REF:
| RESPONSIBILITY: | [5 empty] | ARL. Van Veen
COMMISSIONING DEFECTS Launch Date : | [8 empty] | TASK / JOB | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF | 82
SALOON
| 1 | Telly Mute Not Working
| 2 | Nmma Label Needs To Be Mounted
| 3 | Aircon Switching On Wrong Pump
| 4 | Incomplete Wiring Behind Acdc Panel
| 5 | Incomplete Wiring At Main Saloon Db
| 6 | Saloon Door Needs To Be Set
| 7 | Loose Wires Behind Acdc
| 8 | Bilge Override Lights Not Mounted
| 9 | Genset Isolator Switch Not Mounted
| 10 | Saloon Clear Plastic Db Cover Not Mounted
| 11 | Fire Blanket Not Fitted (Sf)
| 12 | Co2 Sensor Not Mounted
| 13 | saloon door handle loose
| 14 | Inverter Not Programmed On Acdc
| 15 | dual shore power switch light is on even with breaker off
| 16 | genset transfer switch light is on even if breaker is off
| 17 | genset transfer is not working
| 18 | incorrect acdc panel labels
| 19 | small conductor under large conductor x3 behind acdc panel
| 20 | Inverter Alarm Not Working
| 21 | acdc panel closing screws are too short
| 22 | missing negative bus cover in saloon DB
| 23 | saloon downlights not working
| 24 | 4x missing saloon downlights
| 25 | curtacy lights not working
| 26 | multiple loose ground wires in saloon floor
| 27 | morse control ground wire not connected
| 28 | lynxx blue cover missing
| 29 | shunt blue cover missing
| 30 | mast wiring is incomplete
| 31 | missing mounting screws for main breakers in floor
| 32 | missing labels for main breakers in floor
| 33 | house batteries not mounted
| 34 | galley fridge not mounted
| 35 | galley fridge compressor not mounted
| 36 | reefing warning sign not fitted in galley
| 37 | HOB S/S not fitted
| 38 | hand held VHF missing at nav desk
| 39 | no Co-X plugs fitted for VHF antenna
| 40 | MFD needs to be programmed
| 41 | AC Multimeter needs to be programmed
| 42 | No key tallies for saloon door fitted
| 43 | backbone not terminated
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs.
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | ARL. Van Veen |  | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | Page 2 of 5
[5 empty] | HULL NO: |  | C1012
CUST REF:
| RESPONSIBILITY: | [5 empty] | ARL. Van Veen
COMMISSIONING DEFECTS | [9 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
STBD AFT CABIN AND HEADS
| 44 | Leak On Water Heater
| 45 | isolator switch not mounted
| 46 | manual fire suppression wire loose
| 47 | water heater not draining
| 48 | missing bilge labels
| 49 | water heater leaking
| 50 | Missing Salt/Fresh Label At Toilet
| 51 | Toilet Seat Loose
| 52 | Basin Mixer Loose
| 53 | ducting is badly installed in ceiling
STBD MID CABIN AND HEADS
| 54 | not enough light in stbd mid cabin
| 55 | bottom bunk fan mounted to wall not ceiling
| 56 | no usb for reading light
| 57 | water tank is dirty
| 58 | heads extractor fan not working
| 59 | heads rope light not working
| 60 | DB missing rail stopper
| 61 | inboard inspection has a pipe that is not draining properly
| 62 | Waste Tank Indicator Not Working
| 63 | Toilet Seat Loose
STBD FWD CABIN AND HEADS
| 64 | aircon plug not properly connected
| 65 | shower cold water not working
| 66 | fresh water bleed label not fitted
| 67 | depth transducer dummy plug not on boat
| 68 | Toilet Seat Loose
| 69 | Basin Mixer Loose
| 70 | Toilet Anti-Syphen Leaking
| 71 | Missing Salt/Fresh Label At Toilet
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | ARL. Van Veen |  | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | PAGE 3 OF 5
[5 empty] | HULL NO: |  | C1012
CUST REF:
| RESPONSIBILITY: | [5 empty] | ARL. Van Veen
COMMISSIONING DEFECTS | [9 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
PORT FWD CABIN & Heads
| 72 | watermaker was cross wired and is now broken
| 73 | heads light not working
| 74 | watermaker raw water filter not fitted
| 75 | Incorrect Wiring On Finder Relay For Genset
| 76 | no diode for finder relay
| 77 | loose wire hanging in inboard inspection
| 78 | bosch relay is not mounted
| 79 | Toilet Salt/Fresh Is Cross Wired
| 80 | genset battery is not booted
| 81 | genset manufold is at bad location (unable to access)
| 82 | Toilet Seat Loose
| 83 | Basin Mixer Loose
| 84 | Missing Salt/Fresh Label At Toilet
| 85 | Toilet Base Loose
PORT AFT CABIN & Heads
| 86 | Debree In Water Tank
| 87 | cabin lights not working
| 88 | no torque marks on engine isolator
| 89 | reading lights not working
| 90 | water heater not draining
| 91 | missing finder diodes
| 92 | Missing Salt/Fresh Label At Toilet
| 93 | Toilet Seat Loose
| 94 | Basin Mixer Loose
| 95 | toilet pump leaking
| 96 | badly fitted water heater overflow
| 97 | Toilet Base Loose
| 98 | Waste Tank Indicator Not Working
PORT PASSAGE
| 99 | missing blank covers for shore power breaker box
| 100 | Inverter Fans Not Working
| 101 | fresh water bleed leaking
| 102 | missing aircon bleed label
| 103 | aircon filter leaking
| 104 | toilet pump leaking
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | ARL. Van Veen |  | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | PAGE 4 OF 5
[5 empty] | HULL NO: |  | C1012
CUST REF:
| RESPONSIBILITY: | [5 empty] | ARL. Van Veen
COMMISSIONING DEFECTS | [9 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
AFT COCKPIT
| 104 | emergency tiller port side does not engage
| 105 | emergency tiller stbd side gets stuck
| 106 | downlights not working
| 107 | curtacy lights not working
| 108 | david sensor not connected
| 109 | badly installed swim ladder clip
| 110 | gas strut of grill is hitting grill
| 111 | missing warning label at shore power
| 112 | davit motor not booted
| 113 | davit contactor not booted
| 114 | Davit contactor loose
| 115 | poor heat shrink on deck winch terminals
| 116 | missing boots on deck winches
| 117 | missing jammer labels
| 118 | fuel transfer is not working
| 119 | no stbd fuel tank reading
| 120 | raymic wire is not pulled through
| 121 | Battery Link Not Working
| 122 | transom teak steps needs to be fitted
| 123 | liferaft locker backrest supports needs to be fitted
PORT ENGINE ROOM
| 124 | Coolant pipe for water heater damaged
| 125 | genset fuel assist leaking
| 126 | Morse Control Splitpins Not Properly Bent Open
| 127 | single clamps on fuel prefilter
| 128 | missing sterling screw
| 129 | unused shore power lead
| 130 | loose bat neg terminal
| 131 | no battery boots
| 132 | Ecu Not Labeled
| 133 | no heat shrink on gnd wire
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs.
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | ARL. Van Veen |  | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | PAGE 5 OF 5
[5 empty] | HULL NO: |  | C1012
CUST REF:
| RESPONSIBILITY: | [5 empty] | ARL. Van Veen
COMMISSIONING DEFECTS | [9 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
STB ENGINE ROOM
| 134 | rudder gnd wire has no heat shrink
| 135 | bad heat shrink on gnd wire at inboard bus
| 136 | engine harness is suspect (engine dies if tampered with)
| 137 | Morse Control Splitpins Not Properly Bent Open
| 138 | single clamps on fuel prefilter
| 139 | missing blanks in shore power breaker box
| 140 | Ecu Not Labeled
| 141 | Loose sterling cover
| 142 | bad crimps and not heat shrink on galvanic isolator
| 143 | exposed wire on exhaust pipe at engine
| 144 | no battery boots
FWD COCKPIT, SIDE DECKS AND COACH ROOF
| 145 | AR200 cover broken
| 146 | spray dodger is bad design
| 147 | rope painter and blocks not fitted to secure mast
| 148 | coach roof fusion remote not working
| 149 | furler block is mounted too low and line will chafe
| 150 | stbd ceiling panel will chafe against furler rope
| 151 | bottle screws are hitting guard rails
| 152 | missing boots on windlass motor and control box
| 153 | missing windlass junction box
| 154 | wires routed on chain side of bulk head
| 155 | gas locker does not stay open
| 156 | missing gas locker labels
EXTRAS
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs.
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | ARL. Van Veen |  | SIGNATURE:

## C1016
PAGE 1 OF 5
[5 empty] | HULL NO: |  | C1016
CUST REF:
| RESPONSIBILITY: | [5 empty] | ARL. Van Veen
COMMISSIONING DEFECTS Launch Date : | [8 empty] | TASK / JOB | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF | 0
SALOON
| 1 | genset isolator switch not mounted
| 2 | grounding plate in port passgar bilge inboard is not connected to ground
| 3 | 2x amplifiers not fitted
| 4 | saloon fridge door is falling out
| 5 | Saloon clear plastic DB cover not mounted
| 6 | table top not installed
| 7 | fire blanket not fitted (SF)
| 8 | House batteries not booted
| 9 | MFD not showing volts and amps of house battery
| 10 | MFD showing stbd engine bilge is constantly running
| 11 | Main DB not mounted
| 12 | CO2 sensor not mounted
| 13 | autopilot cross wired
| 14 | galley fridge compressor loosely mounted
| 15 | saloon tap weight mounted on wrong side of hose
| 16 | telly mute not working
| 17 | NMMA label needs to be mounted
| 18 | Inverter Alarm Not Working
| 19 | aircon switching on wrong pump
| 20 | VHF wire not pulled through
| 21 | incomplet wiring behind ACDC panel
| 22 | incomplete wiring at main saloon DB
| 23 | aircon not working
| 24 | lights wiring is incomplete
| 25 | saloon door needs to be set
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs.
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | ARL. Van Veen |  | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | Page 2 of 5
[5 empty] | HULL NO: |  | C1016
CUST REF:
| RESPONSIBILITY: | [5 empty] | ARL. Van Veen
COMMISSIONING DEFECTS | [9 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
STBD AFT CABIN AND HEADS
| 26 | aircon not draining
| 27 | cabin, heads and reading lights not working
| 28 | cabin fan not working
| 29 | waste tank indicator light not fitted
| 30 | leak below toilet
| 31 | Toilet Seat Loose
| 32 | missing salt/fresh label at toilet
| 33 | low level bilge float not working
STBD FWD CABIN & HEADS
| 34 | aircon not working
| 35 | cabin, heads and reading lights not working
| 36 | cabin fan not working
| 37 | gas pipes not connected (gas installation incomplete)
| 38 | shower leaking into bilge
| 39 | bidet leaking at wall outlet
| 40 | missing salt/fresh label at toilet
| 41 | waste water tank leaking
| 42 | waste water tank indicator light not working
| 43 | missing salt/fresh label for toilet
| 44 | toilet salt/fresh is cross wired
| 45 | missing c clips on shower rose
| 46 | no 5 amp fuse installed for cabin fan
| 47 | shower cold water leaking
| 48 | deckwash pump running inconsistently
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | ARL. Van Veen |  | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | PAGE 3 OF 5
[5 empty] | HULL NO: |  | C1016
CUST REF:
| RESPONSIBILITY: | [5 empty] | ARL. Van Veen
COMMISSIONING DEFECTS | [9 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
PORT FWD CABIN & Heads
| 49 | aircon not working
| 50 | shower head leaking
| 51 | toilet flush defective
| 52 | clean generator raw water filter
| 53 | cabin heads and reading lights not working
| 54 | cabin fan not working
| 55 | Inverter not powering up
| 56 | Incomplete wiring on DB
| 57 | Incorrect wiring on finder relay for genset
| 58 | Aircon Pump Not Wired
| 59 | cabin door missing a magnet stopper
| 60 | watermaker control box not mounted
PORT AFT CABIN & Heads
| 61 | aircon not working
| 62 | lifting platform DB has a broken grommet at the bottom
| 63 | Cabin Lights Not Working
| 64 | cabin, heads and reading lights not working
| 65 | cabin fan not working
| 66 | leak on water heater hot water
| 67 | radar wire not connected on yachtsense
| 68 | unused cradles at fuel tank
| 69 | debree in water tank
| 70 | shower mixer cross plumbed
| 71 | Toilet Seat Loose
| 72 | Toilet Loose
| 73 | leak on toilet solenoid
| 74 | unwanted screw in basin drain
| 75 | multiple missing fusion remote network cables at DB
| 76 | toilet flush is cross wired
PORT PASSAGE
| 77 | multiple aircon pump pipes leaking
| 78 | missing fuse in HVL under MPPT
| 79 | inverter fans not working
| 80 | waste water tank monitor light not working
| 81 | inverter touch light not working
| 82 | missing bus bar covers and labels
| 83 | aircon connection box not labeled
| 84 | aircon box incorrectly wired
| 84 | Missing timmer module for aircon relays
| 85 | Leak On Basin Plumbing
| 86 | leak on waste water tank
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | ARL. Van Veen |  | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | PAGE 4 OF 5
[5 empty] | HULL NO: |  | C1016
CUST REF:
| RESPONSIBILITY: | [5 empty] | ARL. Van Veen
COMMISSIONING DEFECTS | [9 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
AFT COCKPIT
| 87 | HIN number sticker not fitted
| 88 | stbd sugar scoop bottom curtacy light not working
| 89 | Shore power label not fitted
| 90 | R&C decal label / dome tag
| 91 | jammer labels not fitted
| 92 | loose grommet for port lifting platform up sensor
| 93 | lifting platform stbd sensor is damaged
| 94 | raymic fitting upside down
| 95 | underwater lights not working
PORT ENGINE ROOM
| 96 | battery cover not fitted
| 97 | battery label not fitted
| 98 | junction box labels missing
| 99 | loose clamps on engine fuel prefilter and filter
| 100 | engine fluids low
| 101 | single clamps on fuel lines
| 102 | Ecu Not Labeled
| 103 | single clamps on engine raw water filter
| 104 | Loose wire on starter solenoid
| 105 | galvanic isolator wires loose
| 106 | steering bar laying on raw fibre glass
| 107 | Alternator negative wire not connected
| 108 | morse control cables are badly routed
| 109 | shore power breakers not labeled and no rail stopper
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs.
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | ARL. Van Veen |  | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | PAGE 5 OF 5
[5 empty] | HULL NO: |  | C1016
CUST REF:
| RESPONSIBILITY: | [5 empty] | ARL. Van Veen
COMMISSIONING DEFECTS | [9 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
STB ENGINE ROOM
| 110 | battery cover not fitted and no battery label
| 111 | shore power cable female fittings not properly grommeted
| 112 | junction box labels missing
| 113 | loose clamps on engine fuel prefilter and filter
| 114 | Alternator negative wire not connected
| 115 | single clamps on fuel lines
| 116 | Ecu Not Labeled
| 117 | morse control cables are badly routed
| 118 | engine oil and coolant very low
| 119 | ECU breaker box is loosely mounted
| 120 | coolant pipes for water heater is single clamped
| 121 | engine harness not strapped up
| 122 | loose cradle for fuel piping
| 123 | poor heat shrinks on battery terminals
| 124 | missing cover for ground bus inboard of engine
| 125 | missing labels and loose covers on multiple electrical boxes and junction boxes
| 126 | Loose L-Bracket On Starter Motor
FWD COCKPIT, SIDE DECKS AND COACH ROOF
| 127 | Engine revs do not align
| 128 | No teak steps to coach roof fitted
| 129 | jammer labels not fitted
| 130 | pulleys not fitted (SF)
| 131 | pulleys and rope painter needs to be installed
| 132 | speakers not working
| 133 | boom labels needs to be fitted
| 134 | fwd cockpit speakers not working
| 135 | oven gas shutoff label not fitted
| 136 | Windlass not operational
| 137 | MFD needs to be updated
| 138 | loose wires under windlass motor
| 139 | genset breaker not labeled
| 140 | gas solenoid not wired
EXTRAS
| 141 | aircon display covers (SF)
| 142 | all fire extinguishers to be installed (SF)
| 143 | genset label damaged
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs.
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | ARL. Van Veen |  | SIGNATURE:

## C1010
PAGE 1 OF 5
[5 empty] | HULL NO: |  | C1010
CUST REF:
| RESPONSIBILITY: | [5 empty] | ARL. Van Veen
COMMISSIONING DEFECTS Launch Date : | [8 empty] | TASK / JOB | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF | 0
SALOON
| 1 | Feedback On Autopilot Breaker On Acdc
| 2 | VHF antenna not connected (CO-X plugs on SF)
| 3 | 2x amplifiers on SF
| 4 | LPG monitor mounted skew
| 5 | Saloon clear plastic DB cover not mounted
| 6 | table top not installed
| 7 | fire blanket not fitted (SF)
| 8 | House batteries not booted
| 9 | Lynxx 2 & shunt cover not mounted
| 10 | helm alarm buzzer not mounted
| 11 | Main DB not mounted
| 12 | water pressure pump light on ACDC is flashing
| 13 | saloon tap cross plumbed
| 14 | galley fridge compressor loosely mounted
| 15 | saloon tap weight mounted on wrong side of hose
| 16 | missing reefing label at stbd fwd staircase
| 17 | ACDC panel labeling wrong
| 18 | Engine Return & Supply Pipe Calmp Loose
| 19 | AC multimeter not showing genset voltage and current
| 20 | NMMA label needs to be mounted
| 21 | Inverter Alarm Not Working
| 22 | ACDC panel has no mounting skrews
| 23 | bilge alarm panel loose
| 24 | brken black plastic wire cover behind ACDC panel
| 25 | aircon switching on wrong pump
| 26 | Stbd aircon switches on the wrong LED on the ACDC panel
| 27 | telly mute not working
| 28 | autopilot cross wired
| 29 | delay on 220V cluster from genset switch
| 30 | CO2 sensor not mounted
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs.
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | ARL. Van Veen |  | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | Page 2 of 5
[5 empty] | HULL NO: |  | C1010
CUST REF:
| RESPONSIBILITY: | [5 empty] | ARL. Van Veen
COMMISSIONING DEFECTS | [9 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
STBD AFT CABIN AND HEADS
| 31 | cabin fan cross wired
| 32 | aircon not draining
| 33 | water heater pipes kinked
| 34 | leak on water heater hot water
| 35 | coolant leak on water heater
| 36 | Fuel Tank Brace Loose
| 37 | Toilet Seat Loose
| 38 | missing salt/fresh label at toilet
STBD FWD CABIN & HEADS
| 39 | sniffer wiring not strapped
| 40 | aircon ball valve not labeled
| 41 | depth transducer not labeled
| 42 | missing aircon pump label
| 43 | shower leaking into bilge
| 44 | shower gulley constantly running
| 45 | missing salt/fresh label at toilet
| 46 | waste water tank leaking
| 47 | waste water tank indicator light not working
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | ARL. Van Veen |  | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | PAGE 3 OF 5
[5 empty] | HULL NO: |  | C1010
CUST REF:
| RESPONSIBILITY: | [5 empty] | ARL. Van Veen
COMMISSIONING DEFECTS | [9 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
PORT FWD CABIN & Heads
| 48 | aircon not working
| 49 | shower head leaking
| 50 | toilet flush defective
| 51 | clean generator raw water filter
PORT AFT CABIN & Heads
| 52 | aircon not working
| 53 | aircon display upside down
| 54 | Cabin Lights Not Working
| 55 | Fuel Tank Brace Loose
| 56 | water heater not draining into bilge
| 57 | manual fire suppression wire loose
| 58 | aircon not draining
| 59 | unused cradles at fuel tank
| 60 | debree in water tank
| 61 | shower mixer cross plumbed
| 62 | Toilet Seat Loose
| 63 | Toilet Loose
| 64 | leak on toilet solenoid
| 65 | missing c-clips on fresh water bleed
| 66 | aircon pump outlet piping loose
| 67 | missing aircon pump label
PORT PASSAGE
| 68 | waste water tank monitor light not working
| 69 | leak at aircon bleed valve
| 70 | no aircon bleed labels x3
| 71 | aircon connection box not labeled
| 72 | aircon box incorrectly wired
| 72 | loose wires in bilge outboard
| 73 | toilet pump label badly fitted
| 74 | leak on waste water tank
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | ARL. Van Veen |  | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | PAGE 4 OF 5
[5 empty] | HULL NO: |  | C1010
CUST REF:
| RESPONSIBILITY: | [5 empty] | ARL. Van Veen
COMMISSIONING DEFECTS | [9 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
AFT COCKPIT
| 74 | David Skew
| 75 | HIN number sticker not fitted
| 76 | Strip lights on SF
| 77 | Shore power label not fitted
| 78 | R&C decal label / dome tag
| 79 | jammer labels not fitted
| 80 | david solenoid loosely mounted
| 81 | bad crimps on strip lights bus bar connections
| 82 | raymic fitting upside down
| 83 | horn button not mounted
| 84 | autopilot cover not fitted
| 85 | liferaft locker seat backrest SF
PORT ENGINE ROOM
| 86 | battery cover not fitted
| 87 | battery label not fitted
| 88 | 4x junction box labels missing
| 89 | loose clamps on engine fuel prefilter and filter
| 90 | engine fluids low
| 91 | single clamps on fuel lines
| 92 | Ecu Not Labeled
| 93 | single clamps on engine raw water filter
| 94 | Loose L-Bracket On Starter Motor
| 95 | galvanic isolator wires loose
| 96 | steering bar laying on raw fibre glass
| 97 | AUX stop alarm constantly on
| 98 | Engine Blower Not Working
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs.
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | ARL. Van Veen |  | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | PAGE 5 OF 5
[5 empty] | HULL NO: |  | C1010
CUST REF:
| RESPONSIBILITY: | [5 empty] | ARL. Van Veen
COMMISSIONING DEFECTS | [9 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
STB ENGINE ROOM
| 99 | battery cover not fitted
| 100 | battery label not fitted
| 101 | 4x junction box labels missing
| 102 | loose clamps on engine fuel prefilter and filter
| 103 | Alternator negative wire broken
| 104 | single clamps on fuel lines
| 105 | Ecu Not Labeled
| 106 | altrnator fuse cover loose
| 107 | engine oil very low
| 108 | atlernator temp sensor wire not strapped at sterling
| 109 | coolant pipes for water heater is single clamped
| 110 | engine harness not strapped up
| 111 | loose cradle for fuel piping
| 112 | single clamps on engine raw water filter
| 113 | badly placed clamp on salt waetr pipe connecting to engine coolant compartment
| 114 | loose GND wire on engine connectipon
| 115 | Loose L-Bracket On Starter Motor
FWD COCKPIT, SIDE DECKS AND COACH ROOF
| 116 | windvane to be installed
| 117 | bilge run light at helm not working
| 118 | 12v outlet at helm not working
| 119 | second mast stantions to be fitted
| 120 | pulleys and rope painter needs to be installed
| 121 | speakers not working
| 122 | boom labels needs to be fitted
| 123 | fwd cockpit speakers not working
| 124 | oven gas shutoff label not fitted
| 125 | fwd cockpit door middle handle loose
| 126 | MFD needs to be updated
EXTRAS
| 127 | aircon display covers (SF)
| 128 | all fire extinguishers to be installed (SF)
| 129 | depth transducer gel and wire (SF)
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs.
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | ARL. Van Veen |  | SIGNATURE:

## C1009
PAGE 1 OF 5
[5 empty] | HULL NO: |  | C1009
CUST REF:
| RESPONSIBILITY: | [5 empty] | ARL. Van Veen
COMMISSIONING DEFECTS Launch Date : | [8 empty] | TASK / JOB | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF | 36
SALOON
| 1 | david breaker is a different size to the other breakers
| 2 | genset volts and hertz not set
| 3 | bilge alarm panel not mounted on ACDC
| 4 | outlet at TV not mounted
| 5 | missing boots on deck winch motors
| 6 | curtacy light wiring wrong
| 7 | under basin locker has no catch fitted
| 8 | nav desk front loosely mounted
| 9 | breakers not labeled at house batteries
| 10 | house battery brace loose
| 11 | incorrect jump in main DB at AC wiring
| 12 | missing cover on main negative DC terminal on main DB
| 13 | main DB not mounted
| 14 | main DB has no cover fitted
| 15 | lynxx 2 has no floorboard inspection
| 16 | saloon table not fitted
| 17 | saloon door not properly closing
| 18 | saloon door not properly locking
| 19 | ACDC panel labels incomplete
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs.
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | ARL. Van Veen |  | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | Page 2 of 5
[5 empty] | HULL NO: |  | C1009
CUST REF:
| RESPONSIBILITY: | [5 empty] | ARL. Van Veen
COMMISSIONING DEFECTS | [9 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
STBD AFT CABIN AND HEADS
| 20 | strip light not connected
| 21 | fuel tank level sensor wire not cradled
| 22 | leak on water heater
| 23 | fuel bleed leaking
| 24 | fuel tank level low
| 25 | missing screw on fire boy
| 26 | loose wires inboard in inspection
| 27 | loose morse control cables in inboard inspection
| 28 | aircon not draining properly
| 29 | no catch for cabin door
| 30 | no brackets for bottom cupboards
| 31 | saloon fridge compressor wires not strapped
| 32 | saloon fridge drain not connected
| 33 | david breaker wires loose
| 34 | missing rail stoppers on inboard DB
| 35 | Toilet Anti-Syphen Leaking
| 36 | toilet salt/fresh swopped
| 37 | Toilet Seat Loose
| 38 | Toilet Loose
| 39 | toilet water supply pipe standing proud
| 40 | waste tank bottom pipe damaged
| 41 | waste tank inspection panel not chamfered
| 42 | shower mixer cross plumbed
| 43 | vanity mirror SF
| 44 | waste tank monitor wires not strapped
| 45 | unused cradle above waste tank
STBD FWD CABIN & HEADS
| 46 | 2x missing stoppers on bleed valves in bilge
| 47 | aircon pump outlet pipe not connected
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | ARL. Van Veen |  | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | PAGE 3 OF 5
[5 empty] | HULL NO: |  | C1009
CUST REF:
| RESPONSIBILITY: | [5 empty] | ARL. Van Veen
COMMISSIONING DEFECTS | [9 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
| 48 | depth transducer wire badly layed
| 49 | fresh water leak at freash water pump
| 50 | heads light switch loose
| 51 | toilet salt/fresh crossed
| 52 | Toilet Seat Loose
| 53 | Toilet Loose
| 54 | waste tank indicator light wires not strapped
| 55 | shower leaking into bilge through inspection panel
| 56 | basin mixer leaking
PORT AFT CABIN & Heads
| 57 | missing rope light
| 58 | toilet salt/fresh cross wired
| 59 | Toilet Seat Loose
| 60 | c-clips missing on fresh water bleed
| 61 | unstrapped wiring at yachtsense inspection
| 62 | vanity mirror SF
| 63 | unused network cable in yachtsense inspection
| 64 | defective network cable for fusion fwd cockpit fusion remote
PORT FWD CABIN & Heads
| 65 | genset finder relay wired incorrectly
| 66 | toilet salt/fresh cross wired
| 67 | Basin Mixer Cross Plumbed
PORT PASSAGE
| 68 | aircon pump pipe clamps loose
| 69 | solar panels not giving a reading
| 70 | shower sump pump clamp loose
| 71 | missing stopper on aircon bleed
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | ARL. Van Veen |  | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | PAGE 4 OF 5
[5 empty] | HULL NO: |  | C1009
CUST REF:
| RESPONSIBILITY: | [5 empty] | ARL. Van Veen
COMMISSIONING DEFECTS | [9 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
AFT COCKPIT
| 71 | missing shore power label
| 72 | missing horn button and bilge alarm light at helm station
| 73 | metal tops of deck winches at different angles
| 74 | raymic connection upside down
| 75 | david not catching
| 76 | david switch spelt wrong
PORT ENGINE ROOM
| 77 | single clamps on engine coolant connections
| 78 | no battery top covers
| 79 | No Labels At Filters Outboard
| 80 | no battery label
| 81 | Junction Box Not Labeled
| 82 | stern shower leaking
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs.
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | ARL. Van Veen |  | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | PAGE 5 OF 5
[5 empty] | HULL NO: |  | C1009
CUST REF:
| RESPONSIBILITY: | [5 empty] | ARL. Van Veen
COMMISSIONING DEFECTS | [9 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
STB ENGINE ROOM
| 83 | underwater light ground wire loose
| 84 | sterling wires loose
| 85 | unused grommet on engine ecu breaker
| 86 | single clamps on engine coolant connections
| 87 | no battery top covers
| 88 | No Labels At Filters Outboard
| 89 | no battery label
| 90 | Junction Box Not Labeled
| 91 | HIN number printed under battery box
| 92 | engine mounting paint exfoliating
| 93 | Loose L-Bracket On Starter Motor
FWD COCKPIT, SIDE DECKS AND COACH ROOF
| 94 | incorrect stbd fuel tank level reading
| 95 | missing teflon spacer at fwd cockpit door catch
| 96 | missing oven shutoff label in gas locker
| 97 | windlass slipping
| 98 | missing black plastic piece of windlass
| 99 | fusion remote not picking up network
| 100 | no teflon anti-chafe for anchor chain
EXTRAS
| 101 | Check wrong floorboard layers as previous boat
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs.
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | ARL. Van Veen |  | SIGNATURE:

## C1008
PAGE 1 OF 5
[5 empty] | HULL NO: |  | C1008
CUST REF:
| RESPONSIBILITY: | [5 empty] | ARL. Van Veen
COMMISSIONING DEFECTS Launch Date : | [8 empty] | TASK / JOB | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF | 29
SALOON
| 1 | genset not charging boat
| 2 | bilge low level has an alarm (it should not)
| 3 | bilge indicator panel loose on acdc
| 4 | david breaker not fitted
| 5 | Inverter Not Programmed On Acdc
| 6 | AC meter incorrectly programmed
| 7 | DC meter indicator arrow cross wired
| 8 | missing back cover on ACDC panel
| 9 | Filter Tap Loose
| 10 | HOB not igniting
| 11 | downlights fitted skew
| 12 | lynxx 2 covers not fitted
| 13 | lynxx 2 inspection has no finger hole
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs.
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | ARL. Van Veen |  | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | Page 2 of 5
[5 empty] | HULL NO: |  | C1008
CUST REF:
| RESPONSIBILITY: | [5 empty] | ARL. Van Veen
COMMISSIONING DEFECTS | [9 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
STBD AFT CABIN AND HEADS
| 14 | cabin light wires not pulled through
| 15 | incomplete loose wires above steering pulley
| 16 | toilet salt/fresh switch not labeled
| 17 | toilet salt/fresh water cross plumbed
| 18 | toilet base loose
| 19 | Toilet Seat Loose
| 20 | waste tank outlet pipe badly fitted and kinked
| 21 | Basin Mixer Cross Plumbed
| 22 | shower mixer loose
| 23 | basin hot water leaking
| 24 | Shower Rose Leaking
| 25 | shower mixer backplate not properly sealed
STBD MID CABIN & HEADS
STBD FWD CABIN & HEADS
| 26 | aircon finder relay missing blue clip
| 27 | fresh water bleed has a missing end cap
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | ARL. Van Veen |  | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | PAGE 3 OF 5
[5 empty] | HULL NO: |  | C1008
CUST REF:
| RESPONSIBILITY: | [5 empty] | ARL. Van Veen
COMMISSIONING DEFECTS | [9 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
| 28 | aircon pump outlet clamps loose
| 29 | aircon outlet piping badly layed
| 30 | Toilet Seat Loose
| 31 | Toilet Loose
| 32 | no salt/fresh label for toilet
| 33 | toilet flush switch rubber is exposed and obstructing the switch
| 34 | toilet anti syfen leaking
| 35 | depth transducer fitted skew
PORT AFT CABIN & Heads
| 36 | missing terminator on yachtsense
| 37 | loose pipe clamp on coolant pipe of water heater
| 38 | water heater hot water leaking
| 39 | waste tanl level sensor not working
PORT FWD CABIN & Heads
| 40 | Toilet Seat Loose
| 41 | Toilet Loose
| 42 | missing salt/fresh water label for toilet
| 43 | basin nozzel leaking inconsistant flow
| 44 | fuel leak at genset manifold
| 45 | genset and water maker ballvalves not labeled
PORT PASSAGE
| 46 | aircon pump elbows loose
| 47 | aircon pump outlet leaking at T-piece
| 48 | inverter fans not working
| 49 | missing positive bus cover in HV locker
| 49 | aircon finder relay blue bracket broken
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | ARL. Van Veen |  | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | PAGE 4 OF 5
[5 empty] | HULL NO: |  | C1008
CUST REF:
| RESPONSIBILITY: | [5 empty] | ARL. Van Veen
COMMISSIONING DEFECTS | [9 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
AFT COCKPIT
| 49 | shore power gland loose
| 50 | Swim Ladder Bolts Loose
| 51 | swim ladder catch chaffing
| 52 | david not catching
| 53 | bilge run light not working
| 54 | steaming light not working
| 55 | deck light not working
| 56 | boat number sticker not fitted
PORT ENGINE ROOM
| 57 | Stern Shower Wire Pipe Kinked
| 58 | alternator temp sensor wire broken
| 59 | Fuel Prefilter Pipe Clamps Loose
| 60 | battery top cover missing
| 61 | battery label missing
| 62 | racor fuel filter not labeled
| 63 | engine fluid levels low (coolant, saildrive oil, engine oil)
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs.
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | ARL. Van Veen |  | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | PAGE 5 OF 5
[5 empty] | HULL NO: |  | C1008
CUST REF:
| RESPONSIBILITY: | [5 empty] | ARL. Van Veen
COMMISSIONING DEFECTS | [9 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
STB ENGINE ROOM
| 64 | loose battery terminal
| 65 | no battery top cover
| 66 | no battery label
| 67 | wrong cyrix screws
| 68 | engine fluid levels low (coolant, saildrive oil, engine oil)
| 69 | steering stop rope shackles loose
| 70 | rudder gnd wire heat shrink burnt
| 71 | alternator fuse cover not fitted
| 72 | Loose L-Bracket On Starter Motor
| 73 | underwater light nuts loose
| 74 | fuel prefilter pipes need to be adjusted (badly directed)
FWD COCKPIT, SIDE DECKS AND COACH ROOF
| 75 | deck winches metal tops have different alignments
| 76 | change yachtsense icon placement on mfd
| 77 | nav lights not working
| 78 | genset breaker not labeled
| 79 | coolant present on and below genset
| 80 | loose ancher Lewmar control box terminals
| 81 | loose anchor motor terminals
| 82 | windlass slipping
| 83 | anchor bridle shackels not cable tied
| 84 | anchor bridle hook splitpin not properly bent open
| 85 | anchor chain twisted (not catching on stopper)
| 86 | missing teflon behind fwd cockpit door catch
| 87 | gas solenoid grommet loose
EXTRAS
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs.
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | ARL. Van Veen |  | SIGNATURE:

## C1007
PAGE 1 OF 5
[5 empty] | HULL NO: |  | C1007
CUST REF:
| RESPONSIBILITY: | [5 empty] | A. Labuschagne
COMMISSIONING DEFECTS Launch Date : | [8 empty] | TASK / JOB | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF | 5
SALOON
| 1 | light wiring incorrect (all lights connected to cabin light breaker on acdc)
| 2 | deck winches terminals not booted
| 3 | protruding worm skrews on down lights
| 4 | hob igniter is not working
| 5 | main db breakers not labeled
| 6 | stb aft aircon negative wiring incomplete at main db
| 7 | incorrect ac wiring at main db
| 8 | lynxx 2 terminal wires loose
| 9 | lynxx 2 blue cover not fitted
| 10 | lynxx 2 inspection has no finger cutout
| 11 | incomplete loose wires at main db
| 12 | house battery brace loose
| 13 | missing blade fuses at inverter relays in acdc
| 14 | loose wire on battery protect unit in acdc
| 15 | bilge light unit loose at acdc
| 16 | dc multimeter not working
| 17 | ac multimeter not working
| 18 | loose ac wiring at acdc
| 19 | feedback on acdc panel leds
| 20 | fusion antenna not fitted
| 21 | vhf antenna wire to mast not fitted
| 22 | loose ac outlet at tv bracket
| 23 | carbon monoxide sensor not working
| 24 | stb usb outlet not working
| 25 | loose wires on minibus in ceiling
| 26 | no grey raymic box for vhf mast connection
| 27 | unterminated backbone in aft ceiling
| 28 | ac cluster trips when all items are on on acdc
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs.
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | A. Labuschagne |  | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | Page 2 of 5
[5 empty] | HULL NO: |  | C1007
CUST REF:
| RESPONSIBILITY: | [5 empty] | A. Labuschagne
COMMISSIONING DEFECTS | [9 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
STBD AFT CABIN AND HEADS
| 29 | Cabin Lights Not Working
| 30 | steering pulley bolt not protuding
| 31 | aircon wiring incomplete
| 32 | cut wirin in inboard inspection
| 33 | aft light switch fitted upside down
| 34 | leak on water heater temp control
| 35 | incomplete wiring of reading lights
| 36 | reading lights not working
| 37 | Leak On Shower Plumbing
| 38 | Toilet Fresh Water Solenoid Not Working
| 39 | toilet salt water not working
| 40 | water leaking from toilet bowl
| 41 | missing blue sea cover in ceiling
| 42 | loose wires on minibus in ceiling
| 43 | backbone not termineted in ceiling
| 44 | steering sprocket grommets not tight
| 45 | Basin Mixer Loose
| 46 | carbon monoxide sensor not working
STBD MID CABIN & HEADS
| 47 | carbon monoxide sensor not working
| 48 | cabin light not working
| 49 | reading lights not working
| 50 | loose wires in inboard inspection
| 51 | loose wires in bilge
| 52 | heads light not working
| 53 | loose wires on inboard db
| 54 | unterminated wires on db
| 55 | leak on waste tank
| 56 | toilet salt water not working
| 57 | Toilet Fresh Water Solenoid Not Working
| 58 | ac outlet not fitted
| 59 | Basin Mixer Loose
| 60 | shower rose and mixer loose
STBD FWD CABIN & HEADS
| 61 | carbon monoxide sensor not working
| 62 | cabin light not working
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | A. Labuschagne |  | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | PAGE 3 OF 5
[5 empty] | HULL NO: |  | C1007
CUST REF:
| RESPONSIBILITY: | [5 empty] | A. Labuschagne
COMMISSIONING DEFECTS | [9 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
| 70 | reading lights not working
| 71 | loose wires in inboard inspection
| 72 | loose wires in bilge
| 73 | heads light not working
| 74 | loose wires on inboard db
| 75 | unterminated wires on db
| 76 | leak on waste tank
| 77 | toilet salt water not working
| 78 | Toilet Fresh Water Solenoid Not Working
| 79 | ac outlet not fitted
| 80 | Basin Mixer Loose
| 81 | shower rose and mixer loose
| 82 | timer for aircon pump relay not fitted
PORT AFT CABIN & Heads
| 83 | leak on toilet plumbing
| 84 | Leak On Shower Plumbing
| 85 | Waste Tank Indicator Not Working
| 86 | incomplete wiring at yachtsense
| 87 | autopilot motor cross wired
| 88 | unterminated cut wires at yachtsense
| 89 | cut in shore power cable in inboard inspection
| 90 | Aircon Loose
| 91 | toilet fresh water not working
| 92 | port water pressure pump not working
| 93 | Cabin Lights Not Working
PORT FWD CABIN & Heads
| 94 | Aircon Loose
| 95 | missing dimmer unit in db
| 96 | dimmer unit wiring incomplete at db
| 97 | feedback on rope lights of cabin
| 98 | incorrect fuse used for water lift pump
| 99 | incorrect jump used on finder relay
| 100 | no grey rail stoppers at finder relay
| 101 | loose wires at db
| 102 | Leak On Toilet Plumbing
| 103 | Leak From Shower Into Bilge
PORT PASSAGE
| 104 | hvl extractor fans not fitted
| 105 | leak on waste tank
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | A. Labuschagne |  | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | PAGE 4 OF 5
[5 empty] | HULL NO: |  | C1007
CUST REF:
| RESPONSIBILITY: | [5 empty] | A. Labuschagne
COMMISSIONING DEFECTS | [9 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
AFT COCKPIT
| 105 | morse control nuts loose inside throttle unit
| 106 | seal morse control throttle unit
| 107 | stb fuel tank not showing on mfd
| 108 | prt water tank not showing on mfd
| 109 | port engine bat not showing on mfd
| 110 | genset bat not showing on mfd
| 111 | steering not locking
| 112 | steering stiff
| 113 | raymic connection fitted skew
| 114 | fuel transfer not working
| 115 | Battery Link Not Working
| 116 | fusion remote at helm not working
| 117 | stern light not working
| 118 | david contactor mounting skrew loose
| 119 | incorrect wire types at david bus
| 120 | david switch label spelled wrong
| 121 | wiring unstrapped prt fwd ceiling
| 122 | protruding worm skrew on down lights
| 123 | wiring at ceiling bus wrong type of wires
| 124 | speakers not working
| 125 | ar200 not fitted
PORT ENGINE ROOM
| 126 | blower not working
| 127 | underwater light gnd wire loose
| 128 | steering cable chaffing
| 129 | cyrix not working
| 130 | leak on stern shower
| 131 | shore power earth leakage not labeled
| 132 | galvanic isolator wires loose
| 133 | too many gnd wires on engine
| 134 | sterling settings incorrect
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs.
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | A. Labuschagne |  | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | PAGE 5 OF 5
[5 empty] | HULL NO: |  | C1007
CUST REF:
| RESPONSIBILITY: | [5 empty] | A. Labuschagne
COMMISSIONING DEFECTS | [9 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
STB ENGINE ROOM
| 135 | sterling setting incorrect
| 136 | starter bracket loose
| 137 | inboard draining pipe loose
| 138 | badly routed grounding wires
FWD COCKPIT, SIDE DECKS AND COACH ROOF
| 139 | gaurd rail knoking on shrouds (designer issue)
| 140 | fusion remote in fwd cockpit not working
| 141 | no boots on windlass control box terminals
| 142 | no boots on windlass motor
| 143 | genset blower bolts badly fitted
| 144 | genset oil drain valve leaking
| 145 | leak on jabsco pump on genset
| 146 | rust on genset
| 147 | debree under genset
| 148 | genset earth leakage breaker cross wired
| 149 | missing teflon spacer under camera
| 150 | missing teflon spacer at fwd cockpit door latch
| 151 | fwd cockpit speakers not working
| 152 | fwd cockpit lights not working
EXTRAS
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs.
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | A. Labuschagne |  | SIGNATURE:

## C1006
PAGE 1 OF 5
[8 empty] | HULL NO: |  |  | C1006
CUST REF:
| RESPONSIBILITY: | [9 empty] | A. Labuschagne
COMMISSIONING DEFECTS Launch Date : | [19 empty] | TASK / JOB | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
SALOON
| 1 | AR200 top plastic cover broken
| 2 | TV mounting bracket loose
| 3 | feedback on fan breaker at ACDC
| 4 | feedback on saloon breaker
| 5 | saloon lights on when breaker is off
| 6 | loose AC wiring behind ACDC
| 7 | inverter alarm not working
| 8 | loose wires at battery protect unit
| 9 | poor crimps at battery protect unit
| 10 | saloon and aft cockpit light switches cross wired
| 11 | Loose Wires Behind Acdc
| 12 | loose AC wiring behind ACDC
| 13 | loose gnd bus connections on ac wiring of acdc
| 14 | no power to inverter cluster at acdc
| 15 | wires not terminated on acdc
| 16 | loose screws laying in acdc connectors
| 17 | missing covers on gnd busses in main DB in saloon
| 18 | main DB breakers not labeled
| 19 | unterminated spare wires in main saloon DB
| 20 | Sterlings wired incorrectly ( charging house battery and not Engine )
| 21 | ac meter wired incorrectly (switching on with panel lights Breaker)
| 22 | no rail stopper on main DB in saloon
| 23 | inverter not programmed
| 24 | port engine battery not showing on yacht sense
| 25 | feedback on dc breakers on ac dc
| 26 | 2nd and 3rd ac clusters not working on acdc
| 27 | genset water assist switching on at preheat
| 28 | first ac cluster on acdc switches off when all aircons are switched on
| 29 | loose screw on 2nd lynxx blue cover
| 30 | missing bridges on main saloon DB
| 31 | damaged red bridges in main DB in saloon
| 32 | damaged manual bilge relay in main DB
| 33 | saloon tap red/blue hot cold indicator installed skew
| 34 | unterminated wire at main db in saloon
| 35 | saloon tap weight installed wrong
| 36 | galley fridge compressor mounted loosely
| 37 | loose wire at saloon main DB
| 38 | missing clamp on saloon main fridge drain pipe
| 39 | vhf ant wire not pulled through
| 40 | fwd cockpit strip lights working inconsistently
| 41 | fwd cockpit strip light not working
| 42 | house bat isolator wires loose
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs.
DATE: | [8 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [8 empty] | A. Labuschagne | [7 empty] | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [17 empty] | Page 2 of 5
[8 empty] | HULL NO: |  |  | C1006
CUST REF:
| RESPONSIBILITY: | [9 empty] | A. Labuschagne
COMMISSIONING DEFECTS | [20 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
STBD AFT CABIN AND HEADS
| 43 | cabin fan operating when breaker is off
| 44 | steering pulley damaged
| 45 | aircon not working
| 46 | cabin towel hanger loose
| 47 | not enough thread protruding on steering pulley
| 48 | manual fire suppression wire loose
| 49 | heads door chaffing
| 50 | Toilet Loose
| 51 | Toilet Seat Loose
| 52 | heads bin locker loose
| 53 | poor crimps on wiring on stb aft inboard inspection
| 54 | stb aft shower leak into bilge
| 55 | stb aft toilet salt/fresh crossed
| 56 | engine isolator wires loose
STBD MID CABIN & HEADS
| 57 | cut loom in stb mid cabin inboard inspection
| 58 | ts4-17 & ts4-18 connections on stb mid inboard db has cut wires
| 59 | stb mid heads extractor fan ducting not fitted
| 60 | stb mid cabin carbon monoxide sensor loose
| 61 | stb mid toilet loose
| 62 | stb mid toilet seat loose
| 63 | stb mid basin mixer hot water leaking
| 64 | stb mid db has no stoppers on rails
| 65 | stb mid shower rose leaking
| 66 | stb water tank brace loose
| 67 | stb mid waste tank indicator not wired
STBD FWD CABIN & HEADS
| 68 | stb fwd cabin towel hanger loose
| 69 | stb fwd heads basin mixer loose
| 70 | stb fwd gas sniffer screw loose
| 71 | ac outlet wiring not strapped at bunk head panel stb fwd
| 72 | aircon pump not working stb fwd
| 73 | stb fwd aircon giving fault
| 74 | incorrect wiring for aircon unit at connector box
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs
DATE: | [8 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [8 empty] | A. Labuschagne | [7 empty] | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [17 empty] | PAGE 3 OF 5
[8 empty] | HULL NO: |  |  | C1006
CUST REF:
| RESPONSIBILITY: | [9 empty] | A. Labuschagne
COMMISSIONING DEFECTS | [20 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
| 70 | missing timer relay in stb fwd aircon box
| 71 | leak on toilet salt water plumbing
| 75 | leak on toilet salt water pump
| 76 | leak from shower sump into bilge
| 77 | waste tank level monitor not mounted
| 78 | toilet salt/fresh cross wired
PORT PASSAGE
| 79 | prt aircon wiring incomplete | prt aircon wiring incomplete | prt aircon wiring incomplete | prt aircon wiring incomplete | prt aircon wiring incomplete | prt aircon wiring incomplete | prt aircon wiring incomplete | prt aircon wiring incomplete | prt aircon wiring incomplete | prt aircon wiring incomplete | prt aircon wiring incomplete | prt aircon wiring incomplete | prt aircon wiring incomplete | prt aircon wiring incomplete | prt aircon wiring incomplete | prt aircon wiring incomplete | prt aircon wiring incomplete | prt aircon wiring incomplete
| 80 | prt aircon timer at relay not fitted
| 81 | leak on aircon blead valve prt side
| 82 | prt aft heads anti syphon leaking
| 83 | prt fwd heads anti syphon leaking
| 84 | leak in top of prt waste tank
| 85 | waste tank monitoring light not working prt | waste tank monitoring light not working prt | waste tank monitoring light not working prt | waste tank monitoring light not working prt | waste tank monitoring light not working prt | waste tank monitoring light not working prt | waste tank monitoring light not working prt | waste tank monitoring light not working prt | waste tank monitoring light not working prt | waste tank monitoring light not working prt | waste tank monitoring light not working prt | waste tank monitoring light not working prt | waste tank monitoring light not working prt | waste tank monitoring light not working prt | waste tank monitoring light not working prt | waste tank monitoring light not working prt | waste tank monitoring light not working prt | waste tank monitoring light not working prt
PORT AFT CABIN & Heads
| 86 | leak on water heater hot water outlet in prt aft cabin
| 87 | kink in prt fuel tank sensor wire
| 88 | prt engine isolator terminals loose
| 89 | prt aft inboard reading light loose
| 90 | leak on prt aircon pump
| 91 | prt aft heads basin loose
| 92 | prt aft basin cross plumbed
| 93 | leak on prt aft shower mixer
| 94 | prt aft shower mixer mounted loosely
| 95 | prt aft toilet salt/fresh cross wired | prt aft toilet salt/fresh cross wired | prt aft toilet salt/fresh cross wired | prt aft toilet salt/fresh cross wired | prt aft toilet salt/fresh cross wired | prt aft toilet salt/fresh cross wired | prt aft toilet salt/fresh cross wired | prt aft toilet salt/fresh cross wired | prt aft toilet salt/fresh cross wired | prt aft toilet salt/fresh cross wired | prt aft toilet salt/fresh cross wired | prt aft toilet salt/fresh cross wired | prt aft toilet salt/fresh cross wired | prt aft toilet salt/fresh cross wired | prt aft toilet salt/fresh cross wired | prt aft toilet salt/fresh cross wired | prt aft toilet salt/fresh cross wired | prt aft toilet salt/fresh cross wired
| 96 | saloon aircon not draining
PORT FWD CABIN & Heads
| 97 | fuel leak on genset manifold
| 98 | prt fwd inboard db spare wires not terminated
| 99 | genset ac wiring incomplete prt fwd inboard db
| 100 | prt fwd heads basin mixer loose | prt fwd heads basinmixer loose | prt fwd heads basinmixer loose | prt fwd heads basinmixer loose | prt fwd heads basinmixer loose | prt fwd heads basinmixer loose | prt fwd heads basinmixer loose | prt fwd heads basinmixer loose | prt fwd heads basinmixer loose | prt fwd heads basinmixer loose | prt fwd heads basinmixer loose | prt fwd heads basinmixer loose | prt fwd heads basinmixer loose | prt fwd heads basinmixer loose | prt fwd heads basinmixer loose | prt fwd heads basinmixer loose | prt fwd heads basinmixer loose | prt fwd heads basinmixer loose
| 101 | bus bar connected incorrectly
| 102 | bridge wrong way on prt fwd inboard db
| 103 | prt fwd toilet salt fresh cross wired
| 104 | incorrect wire used on genset fuel lift relay
| 105 | water maker getting constant power
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs
DATE: | [8 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [8 empty] | A. Labuschagne | [7 empty] | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [17 empty] | PAGE 4 OF 5
[8 empty] | HULL NO: |  |  | C1006
CUST REF:
| RESPONSIBILITY: | [9 empty] | A. Labuschagne
COMMISSIONING DEFECTS | [20 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
AFT COCKPIT
| 105 | helm seat backing loose
| 106 | steering stiff
| 107 | fusion remote at helm not connected
| 108 | raymic fitting skew
| 109 | david skew
| 110 | wrong david switch
| 111 | swim ladder bolts loose
| 112 | stern shower tap mounted skew
PORT ENGINE ROOM
| 113 | fuel lines badly layed prt engine
| 114 | alternator wiring not strapped
| 115 | loose wires on galvanic isolator
| 116 | cyrix not getting power
| 117 | no cover for engine battery
| 118 | no strap for engine battery
| 119 | too many gnd wires on engine connection
| 120 | single clamp on engine impeller connector
| 121 | engine harness wires not strapped
| 122 | loose single wire of engine harness
| 123 | unused bung in port engine room
| 124 | loose nut on ref throttle
| 125 | stern shower leaking
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs.
DATE: | [8 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [8 empty] | A. Labuschagne | [7 empty] | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [17 empty] | PAGE 5 OF 5
[8 empty] | HULL NO: |  |  | C1006
CUST REF:
| RESPONSIBILITY: | [9 empty] | A. Labuschagne
COMMISSIONING DEFECTS | [20 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
STB ENGINE ROOM
| 126 | no cover on engine fuse stb
| 127 | poor heat shrink on sterling wiring
| 128 | no battery cover
| 129 | no battery strap
| 130 | cyrix mounting skrew loose
| 131 | underwater light light nuts loose
FWD COCKPIT, SIDE DECKS AND COACH ROOF
| 132 | guard rails loose
| 133 | side deck teak step metal supports loosely mounted
EXTRAS
| 134 | Electrical Anthena not fitted SF
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs.
DATE: | [8 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [8 empty] | A. Labuschagne | [7 empty] | SIGNATURE:

## C1005
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | PAGE 1 OF 5
[5 empty] | HULL NO: |  | C1005
CUST REF:
| RESPONSIBILITY: | [5 empty] | A. Labuschagne
COMMISSIONING DEFECTS Launch Date : | [8 empty] | TASK / JOB | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
SALOON
| 1 | Inverter not switching off at display
| 2 | inverter switch not working
| 3 | inverter not programmed on ACDC
| 4 | inverter alarm not working
| 5 | inverter alarm relays not fitted
| 6 | watermaker not wired
| 7 | touchlight in high voltage locker not working
| 8 | loose wires behind ACDC
| 9 | bilge override lights not working
| 10 | prt high water not working
| 11 | aircon pump not wired
| 12 | GND wires behind ACDC are cut
| 13 | Low water pressure at basin
| 14 | induction HOB incorrectly labeled and label is damaged on ACDC
| 15 | no power to genset starter panel on ACDC
| 16 | HOB knobs not fitted
| 17 | missing terminator on backbone at MFD
| 18 | missing cover on blue sea negative bus
| 19 | loose wires on floor DB
| 20 | loose live wires on main DB
| 21 | loose wires on negative bus in DB
| 22 | poor crimps on wires in main DB
| 23 | damaged bridge on main DB
| 24 | loose battery distributer unit
| 25 | different battery terminals used
| 26 | filter tap fitted wrong (too tight)
| 27 | galley fridge not working
| 28 | Saloon & Aft cockpit lights crossed
| 29 | Saloon, aft cockpit & flybridge curtacy lights crossed
| 30 | Main LPG control incorrectly wired
| 31 | feedback on autopilot breaker on ACDC
| 32 | bilge pumps not working all over
| 33 | incorrectly wired bilge alarms
| 34 | HOB fitted skew
STBD AFT CABIN AND HEADS
| 35 | aircon pump not wired
| 36 | toilet salt/fresh water crossed
| 37 | toilet fresh water solenoid not working
| 38 | toilet hardup against wall
| 39 | poor heat shrink on stb engine isolator switch
| 40 | loose manual fire suppression wire
| 41 | leak on stb water pressure pump plumbing
| 42 | fridge compressor not mounted
| 43 | stb high water float alarm not working
| 44 | fuel tank brace loose
| 45 | water tank brace loose
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs.
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | A. Labuschagne |  | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | Page 2 of 5
[5 empty] | HULL NO: |  | C1005
CUST REF:
| RESPONSIBILITY: | [5 empty] | A. Labuschagne
COMMISSIONING DEFECTS | [9 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
STBD MID CABIN & HEADS
| 46 | heads extractor fan not fitted
| 47 | heads extractor fan ducting incomplete
| 48 | waste tank refill pipe leaking
| 49 | waste water tank full indicator wire not strapped
| 50 | toilet seat loose
| 51 | house bat isolator switch missing a mounting skrew
| 52 | poor crimp on heads strip light
| 53 | missing fuse on stb mid inboard
| 54 | stb mid basin loose
| 55 | toilet salt/fresh water switch not working
| 56 | shower mixer pipe kinked
STBD FWD CABIN & HEADS
| 57 | aircon pump not wired
| 58 | AC outlet not wired up
| 59 | gas locker sniffer not working
| 60 | toilet loose
| 61 | toilet seat loose
| 62 | leak on top of waste water tank
| 63 | toilet anti-syphen leaking
| 64 | toilet fresh water solenoid not working
| 65 | toilet fresh/salt switch crossed
| 66 | waste water tank full indicator not working
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | A. Labuschagne |  | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | PAGE 3 OF 5
[5 empty] | HULL NO: |  | C1005
CUST REF:
| RESPONSIBILITY: | [5 empty] | A. Labuschagne
COMMISSIONING DEFECTS | [9 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
PORT PASSAGE
| 67 | waste tank full indicator not wired
| 68 | watermaker breaker not installed in high voltage locker
| 69 | water maker negative terminal not connected in high voltage locker
| 70 | waste tank plumbing in bilge not strapped
PORT AFT CABIN
| 71 | aircon pump not wired
| 72 | loose wires on fireboy black boxes
| 73 | cabin strip light wires not terminated
| 74 | Quattro bypass switch not mounted
| 75 | yachtsense DB mounted skew
| 76 | loose wires at inboard DB
| 77 | aircon mounted loosely
| 78 | fuel tank brace loose
| 79 | water tank brace loose
PORT AFT HEADS
| 80 | toilet hardup against wall
| 81 | toilet fresh water not working
PORT FWD CABIN
| 82 | aircon pump not wired
| 83 | aircon drain pipe clamp loose
| 84 | genset fuel assist not switching on at preheat
| 85 | loose wire on water lift relay of genset
| 86 | missing crimp on AC wiring for genset water lift pump relay
| 87 | AC outlet fitted upside down
| 88 | missing clamp on genset water assist pump
PORT FW HEADS
| 89 | toilet seat skew
| 90 | shower rose cold water kinked
| 91 | basin mixer pipes kinked
| 92 | salt/fresh water for toilet cross wired
| 93 | basin mixer loose
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | A. Labuschagne |  | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | PAGE 4 OF 5
[5 empty] | HULL NO: |  | C1005
CUST REF:
| RESPONSIBILITY: | [5 empty] | A. Labuschagne
COMMISSIONING DEFECTS | [9 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
AFT COCKPIT
| 93 | yachtsense fuel and water showing incorrectly on MFD
| 94 | steering bar knocking
| 95 | autopilot reference cross wired
| 96 | autopilot motor cross wired
| 97 | david skew
| 98 | swim ladder bolts loose
| 99 | fridge not working
| 100 | battery link not working
| 101 | fuel transfer not working
| 102 | shore water connector leaking
| 103 | loose wires on aft cockpit ceiling mini bus
| 104 | david relay wiring loose
| 105 | no boots on david relay wiring
| 106 | david motor terminals loose
| 107 | victro not setup or connected to MFD
| 108 | autopilot motor not working
PORT ENGINE ROOM
| 109 | GND wires not sleeved
| 110 | Too many wires connected to engine ground connection
| 111 | steering cable loose
| 112 | engine blower not working
| 113 | fire suppression incorrectly wired
| 114 | touch light not working
| 115 | engine fuse terminal broken
| 116 | engine fuse not covered
| 117 | leak on muffler pipe connector
| 118 | morse control splitpins not properly bent open
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs.
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | A. Labuschagne |  | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | PAGE 5 OF 5
[5 empty] | HULL NO: |  | C1005
CUST REF:
| RESPONSIBILITY: | [5 empty] | A. Labuschagne
COMMISSIONING DEFECTS | [9 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
STB ENGINE ROOM
| 119 | GND wires not sleeved
| 120 | Too many wires connected to engine ground connection
| 121 | steering cale loose
| 122 | cyrix relay not working
| 123 | cyrix wires loose
| 124 | engine blower not working
| 125 | fire suppression incorrectly wired
| 126 | starter L-bracket loose
| 127 | engine fuse terminal loose
| 128 | engine fuse not covered
| 129 | touch light not working
| 130 | poor crimp on GND wire on rudder
| 131 | engine raw water filter clamp loose
| 132 | fuel clamps loose on prefilter
FWD COCKPIT, SIDE DECKS AND COACH ROOF
| 133 | small hatch next to genset slams closed and does not latch
| 134 | fwd cockpit strip light inconsistant switching
| 135 | fwd cockpit strip light loose in enclosure producing inconsistant lighting
| 136 | genset red start switch on genset cover panel not wired up
| 137 | genset fuel pump wiring not properly insolated
| 138 | windlass slipping
| 139 | fwd cockpit remote not wired up
| 140 | aft cockpit remote not wired up
| 141 | Camara Not Wired up
EXTRAS
| 142 | no torque marks on A-frames
| 143 | Extractor Fans Not working in HVL
| 144 | VHF Anthenna Wire not pulled through
| 145 | Mid Ship Heads Port side Waste tank light not working
| 146 | Neatrals not connected on AC board
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs.
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | A. Labuschagne |  | SIGNATURE:

## C1004
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | PAGE 1 OF 5
[5 empty] | HULL NO: |  | C1004
CUST REF:
| RESPONSIBILITY: | [5 empty] | A. Labuschagne
COMMISSIONING DEFECTS Launch Date : | [8 empty] | TASK / JOB | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
SALOON
| 1 | Genset Isolator switch loose
| 2 | Dc M2 display not working
| 3 | AC M2 display not working
| 4 | Genset starter harness not wired
| 5 | Genset starter harness plug broken
| 6 | Fresh water pump signals not showing/working
| 7 | Incorrect wiring on fresh water pumps at DB board
| 8 | High level alarm present while present over-ride button
| 9 | Loose DC wires on panel board
| 10 | Loose AC wires on panel board
| 11 | No Relays fitted for inverter alarm
| 12 | Inverter alarm not working
| 13 | Loose wires on battery protect unit
| 14 | Numerous QC green stickers present
| 15 | Loose switches at TV-Bracket
| 16 | Missing cover/Loose negative shunt
| 17 | Loose cover on battery distributor
| 18 | Missing cover on lewmar breaker
| 19 | Oven Loose
| 20 | LPG not wired
| 21 | No power to Galley fridge
| 22 | Loose filter tap/damaged
| 23 | Galley fridge compressor loose
| 24 | Missing covers on buss at TV-Bracket locker
| 25 | Monoxide detector not working
| 26 | Loose Backbone in ceiling
| 27 | Missing terminators on backbone in ceiling
| 28 | Bilge pump incorrectly wired
| 29 | Wires nor pulled through for lights
| 30 | Loose wires on Mini buss in ceiling
| 31 | Missing boots on lewmar winches
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs.
DATE:
COMMISSIONING ENGINEER: | [5 empty] | A. Labuschagne |  | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | Page 2 of 5
[5 empty] | HULL NO: |  | C1004
CUST REF:
| RESPONSIBILITY: | [5 empty] | A. Labuschagne
COMMISSIONING DEFECTS | [9 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
STBD AFT Cabin & Heads
| 32 | Loose fridge compressor
| 33 | Fire suppression cable loose
| 34 | Leak on water heater
| 35 | lights not working
| 36 | No wires puled through for lights
| 37 | Heads lights switch/wiring wrong
| 38 | Inboard reading light not working
| 39 | Outboard reading light not working
| 40 | Leak from shower into bilge
| 41 | Toilet water supply not working, Salt and Fresh
| 42 | Leak on toilet plumbing
| 43 | Basin mixer loose
STBD MID-SHIPS
| 44 | Poor airflow from air vent
| 45 | poor crimps on outlets
| 46 | Lights not working
| 47 | No wires pulled through for lights
| 48 | Leak from waste tank
| 49 | Toilet water supply not working, Fresh and Salt
| 50 | Anti-syphon loops leaking
| 51 | Basin mixer loose
| 52 | Heads lights not working
| 53 | Waste tank indicator not working
| 54 | Incomplete wiring on inboard buss
| 55 | Poor crimps on inboard Buss
STBD FWD. CABIN & HEADS
| 56 | Aircon nor wired up
| 57 | Missing Relay for Aircon
| 58 | Lights not working
| 59 | wires not pulled through for lights
| 60 | Heads Lights not working
| 61 | Waste tank monitor not working
| 62 | Toilet water supply not working, Salt and fresh
| 63 | Leak on toilet plumbing
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs
DATE:
COMMISSIONING ENGINEER: | [5 empty] | A. Labuschagne |  | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | PAGE 3 OF 5
[5 empty] | HULL NO: |  | C1004
CUST REF:
| RESPONSIBILITY: | [5 empty] | A. Labuschagne
COMMISSIONING DEFECTS | [9 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
| 64 | Basin mixer loose
| 65 | Leak on Shower plumbing
PRT FWD. CABIN
| 66 | Aircon Loose
| 67 | Ducting poorly fitted
| 68 | Genset battery wiring incomplete
| 69 | Broken distribution board covers
| 70 | Missing RELAY for genset wiring
| 71 | Genset raw water pump not working
| 72 | Aircon wiring incomplete
| 73 | Lights not working
| 74 | No wiring pulled through for lights
| 75 | Aft light stays on continuously
| 76 | Touch light not working
| 77 | Poor crimps on plug wiring
PRT FWD. HEADS
| 78 | Shower sump not working
| 79 | Toilet waste supply not working
| 80 | Basin mixer loose
| 81 | Leak on toilet plumbing
| 82 | Lights not working
PRT PASSAGE AND STAIRS
| 83 | Incomplete wiring on breaker box
| 84 | Broken Ball valve
| 85 | Missing covers in HVL
| 86 | Leak From shower pumps
| 87 | Leak on water pressure pump plumbing
PRT AFT HEADS
| 88 | Toilet pumps not working
| 80 | Basin mixer loose
| 90 | Leak on toilet plumbing
| 91 | Waste tank indicator not working
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs
DATE:
COMMISSIONING ENGINEER: | [5 empty] | A. Labuschagne |  | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | PAGE 4 OF 5
[5 empty] | HULL NO: |  | C1004
CUST REF:
| RESPONSIBILITY: | [5 empty] | A. Labuschagne
COMMISSIONING DEFECTS | [9 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
PRT AFT CABIN
| 92 | Lights not working
| 93 | Wires not pulled through for lights
| 94 | hact-cense wiring incomplete
| 95 | Engine Battery switch incomplete/LOOSE
| 96 | Leak from shower into bilge
| 97 | No wire for water tank transducer
| 98 | Loose wires on fire buoy busses
AFT COCKPIT
| 99 | Engine throttles not aligned
| 100 | Steering stiff
| 101 | Steering chain slipping
| 102 | Davit skew
| 103 | Auto-pilot/rudder ref wired incorrectly
| 104 | Strip lights not working
| 105 | Down lights not working
| 106 | Wires not pulled through for lights
| 107 | Aft cockpit fridge not working
| 108 | Raymic fittings not fitted
| 109 | Horn switch & bilge light not working
| 110 | Fuel transfer pump not working
PRT ENGINE ROOM
| 111 | Engine fuse wires loose
| 112 | Poor crimps on galvanic isolator
| 113 | No heat shrink on galvanic isolator wires
| 114 | Leak on stern shower
| 115 | Loose plumbing on inboard drain pipe
| 116 | Loose wires on sterling
| 117 | Under water light not working
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs.
DATE:
COMMISSIONING ENGINEER: | [5 empty] | A. Labuschagne |  | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | PAGE 5 OF 5
[5 empty] | HULL NO: |  | C1004
CUST REF:
| RESPONSIBILITY: | [5 empty] | A. Labuschagne
COMMISSIONING DEFECTS | [9 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
STB ENGINE ROOM
| 118 | Loose wires on sterling
| 119 | Loose wires on starter bracket
| 120 | loose wires on engine starter battery fuse
| 121 | fuel filter loose
| 122 | Incorrect settings on sterling
FWD. COCKPIT, SIDE DECKS AND COACH ROOF
| 123 | Genset not working
| 124 | Fusion radio not working
| 125 | incomplete wiring in genset locker
| 126 | flybridge fusion remote not working
| 127 | Leak on genset raw water plumbing
Extra:
| 128 | Prt aft cabin aircon in ceiling loose
| 129 | Prt aft cabin aft aircon loose
| 130 | Battery link not working
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs.
DATE:
COMMISSIONING ENGINEER: | [5 empty] | A. Labuschagne |  | SIGNATURE:

## C1003
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | PAGE 1 OF 5
[5 empty] | HULL NO: |  | C1003
CUST REF:
| RESPONSIBILITY: | [5 empty] | A. Labuschagne
COMMISSIONING DEFECTS Launch Date : | [8 empty] | TASK / JOB | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
SALOON
| 1 | Down light switch cross wired
| 2 | No labels of fridges on AC/DC panel
| 3 | Down light grommet worm screws not flush
| 4 | Yachtsense to be programmed
| 5 | Missing stainless steel catch at AC/DC
| 6 | Generator not giving power
| 7 | Water pressure pump light not showing on AC/DC
| 8 | Water pressure hot wired
| 9 | HOB fitted skew
| 10 | DB not mounted
| 11 | Poor crimp on blue sea bus at DB compromised
| 12 | Black wire to be terminated in DB
| 13 | Poor heat shrink on AC wire in DB
| 14 | Damaged bridges on DB
| 15 | MFD stays on when breaker is switched off
| 16 | Inverter buzzer not working when house battery is switched off
| 17 | Relays not fitted
| 18 | Manual bilge pump overrides cross wired
| 19 | Buzzers working with low water running
| 20 | Stb watre tank not showing
| 21 | House battery not showing volts
| 22 | gensetbattery not showing
| 23 | No network cable by MFD
STBD AFT CABIN AND HEADS
| 24 | Fan not connected
| 25 | fridge compressor not secured
| 26 | inboard reading light loose
| 27 | manual suppression wire gromet loose
| 28 | water heater not properly mounted
| 29 | Fuel tank sensor wire loose
| 30 | fuel pipes metal support loose
| 31 | manual suppression wire nut loose
| 32 | aft aircon loose
| 33 | high level float not muting music
| 34 | fridge drain not fitted properly
| 35 | leak on shower plumbing
| 36 | no terminator fitted in backbone in ceiling
| 37 | basin mixer loose
STBD MID CABIN & HEADS
| 38 | basin mixer loose
| 39 | Tank level sensor not connected
| 39 | waste tank monitor not connected
| 40 | leak on aft toilet anti-syphen
| 41 | poor crimp on aft toilet solenoid
| 42 | water tank brace loose
| 43 | extraction fan not connected
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs.
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | A. Labuschagne |  | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | Page 2 of 5
[5 empty] | HULL NO: |  | C1003
CUST REF:
| RESPONSIBILITY: | [5 empty] | A. Labuschagne
COMMISSIONING DEFECTS | [9 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
STBD FWD CABIN & HEADS
| 44 | basin mixer loose
| 45 | leak on hot water t-piece in bilge
| 46 | leak on waste water tank
| 47 | leak on shower mixer
| 48 | toilet anti-syphen leaking
| 49 | aircon not connected
| 50 | aircon loose
PORT FWD CABIN
| 51 | Strip light wire visible
| 52 | Strip light loose
| 53 | Aircon loose
| 54 | Pump backboard in bilge not properly secured
| 55 | Poorly strapped wiring on genset exhaust outlet
| 56 | Raw wire on aft strip light
| 57 | Wires inboard on DB not terminated
| 58 | Book shelf loose
| 59 | Inboard reading light loose
| 60 | Cabin towel hanger loose
| 61 | Aircon does not have a drain
| 62 | Aircon vent connection loose
| 63 | Genset battery terminal loose
| 64 | GFCI outlet to be mounted properly
PORT FW HEADS
| 65 | Sower sump not working
| 66 | Toilet loose
| 67 | Set port water pressure
| 68 | Mount toilet switch
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | A. Labuschagne |  | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | PAGE 3 OF 5
[5 empty] | HULL NO: |  | C1003
CUST REF:
| RESPONSIBILITY: | [5 empty] | A. Labuschagne
COMMISSIONING DEFECTS | [9 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
PORT PASSAGE
| 69 | Fresh water pump t-piece leaking
| 70 | Bad plumbing layout at fresh water pump
| 71 | toilet anti-syphen leaking
| 72 | waste tank top pipes leaking
| 73 | shower pump leaking
| 74 | extractor fan in high voltage locker not working
| 75 | Inverter loose
| 76 | positive bus bar too close to inverter
| 77 | breaker box loose
| 78 | transformer loose
| 79 | missing cover on blue sea bus
| 80 | waste water tank sensor not connected
PORT AFT CABIN
| 81 | Water tank sensor wire badly layed
| 82 | Aircon duckting incomplete in ceiling
| 83 | Missing terminator on backbone in ceiling
| 84 | Aft aircon not draining properly
| 85 | Aft light switch fitted upside down
| 86 | Manual suppression wire grommet fitted poorly
| 87 | Isolator switch skew
| 88 | Isolator switchwiring loose
| 89 | Poorly fitted outboard reading light
| 90 | drain pipe loose in aft ceiling
| 91 | Loose wire on fireboy system top corner
| 92 | Aircon spare power cable not terminated
| 93 | busbar not labeled by yachtsense in inboard inspection
| 94 | water tank brace loose
| 95 | ACU 400 giving constant power to backbone
| 96 | ACU 400 cross wired
| 97 | 5 way back bone connected to constant power
| 95 | fuel return ball valve loose on tank
PORT AFT HEADS
| 98 | Strip light not connected
| 99 | Basin mixer loose
| 100 | Toilet loose
| 101 | Salt/Fresh water cross wired
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | A. Labuschagne |  | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | PAGE 4 OF 5
[5 empty] | HULL NO: |  | C1003
CUST REF:
| RESPONSIBILITY: | [5 empty] | A. Labuschagne
COMMISSIONING DEFECTS | [9 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
AFT COCKPIT
| 101 | David switch not mounted
| 102 | No cable ties on david shackels
| 103 | David is skew
| 104 | David sensor fitted upside down
| 105 | Autopilot screen fitted skew
| 106 | MFD backplate loose
| 107 | Raymic connector upside down
| 108 | Stb & Prt handrails loose
| 109 | Stb top curtacy light not connected and badly fitted
| 110 | Port winch rope outlet not at correct angle
| 111 | Swim ladder skew and chaffing
| 112 | Swim ladder catch hitting
| 113 | Stern shower leaking on cold water pipe
| 114 | Stern shower leaking at nozzle
| 115 | Stern shower wire pipe kinked
| 116 | Stern shower wire pipe kinked
| 117 | Stern floor board port side not flush with floor
| 118 | Gap at hinge of inspection above fridge
| 119 | Inspection above fridge, latch not fitted
| 120 | Strip lights inconsistant (Showing individual LED's)
| 121 | David motor terminals loose
| 122 | David solenoid terminals loose
| 123 | Small blue wire at david motor not terminated
| 124 | David pully stiff at rope outlet
| 125 | AR200 fitted wrong way
| 126 | Dome nuts to be fitted on david bottom bolts
PORT ENGINE ROOM
| 127 | engine starter bracket loose
| 128 | too many terminals on engine stud
| 129 | grounding wire on under water light loose
| 130 | poor crimp on galvanic isolator wires
| 131 | Exhaust temp open circuit
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs.
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | A. Labuschagne |  | SIGNATURE:
|  |  | 24. COMMISSIONING EXCEPTION SHEET | [6 empty] | PAGE 5 OF 5
[5 empty] | HULL NO: |  | C1003
CUST REF:
| RESPONSIBILITY: | [5 empty] | A. Labuschagne
COMMISSIONING DEFECTS | [9 empty] | REPR BY (NAME) | COMPL DT | T/L Sign | CE SIGN-OFF
STB ENGINE ROOM
| 132 | gas lockert drain outlet loose
| 133 | too many terminals on engine stud
| 134 | loose terminals on positive bus on battery
| 135 | engine starter bracket loose
| 136 | engine starter positive wire loose
FWD COCKPIT, SIDE DECKS AND COACH ROOF
| 137 | topping lift block making clucking sound
Extras
The Commissioning Engineer has to list all defects found on the boat after launch within 24hrs.
DATE: | [5 empty] | 2025-06-24
COMMISSIONING ENGINEER: | [5 empty] | A. Labuschagne |  | SIGNATURE:

## Common_Defect_List
Common Defect List | Task Allocation | Saloon | Stbd Aft | Stbd Mid | Stbd Fwd | Prt Aft | Prt Passage | Prt Fwd | Aft Cockpit | Prt Engine Room | Stb Engine Room | FWD COCKPIT, SIDE DECKS AND COACH ROOF | Extras | Area Allocation | Task Allocation
Leak On Basin Plumbing | PLUM | Yes | Yes | Yes | Yes | Yes |  | Yes | [5 empty] | Yes | PLUM
Basin Mixer Loose | PLUM | Yes | Yes | Yes | Yes | Yes |  | Yes | [6 empty] | ELEC
Basin Cross Plumbed | PLUM | Yes | Yes | Yes | Yes | Yes |  | Yes | [6 empty] | MECH
Junction Box Not Labeled | ELEC | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  |  | FA
Strip Lights Not Working | ELEC | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  |  | Yes |  |  | DECK
Inverter Not Programmed On Acdc | ELEC | Yes | [12 empty] | CARP
Inverter Alarm Not Working | ELEC | Yes
Watermaker Not Wired | ELEC | Yes | [5 empty] | Yes
Loose Wires Behind Acdc | ELEC | Yes
Bilge Override Lights Not Working | ELEC | Yes
Filter Tap Fitted Wrong (Too Tight) | PLUM | Yes
Galley Fridge Not Working | ELEC | Yes
Genset Isolator Switch Not Mounted | CARP | Yes
2X Amplifiers Not Fitted | ELEC | Yes
Saloon Clear Plastic Db Cover Not Mounted | FA | Yes
Table Top Not Installed | CARP | Yes
Fire Blanket Not Fitted (Sf) | CARP | Yes
House Batteries Not Booted | ELEC | Yes
Mfd Not Showing Volts And Amps Of House Battery | ELEC | Yes | [6 empty] | Yes
Co2 Sensor Not Mounted | CARP | Yes
Autopilot Cross Wired | ELEC | Yes | [6 empty] | Yes
Galley Fridge Compressor Loosely Mounted | CARP | Yes
Saloon Tap Weight Mounted On Wrong Side Of Hose | PLUM | Yes
Telly Mute Not Working | ELEC | Yes
Nmma Label Needs To Be Mounted | FA | Yes
Inverter Alarm Not Working | ELEC | Yes
Aircon Switching On Wrong Pump | ELEC | Yes | Yes |  | Yes | Yes |  | Yes
Incomplete Wiring Behind Acdc Panel | ELEC | Yes
Incomplete Wiring At Main Saloon Db | ELEC | Yes
Aircon Not Working | ELEC | Yes | Yes |  | Yes | Yes |  | Yes
Saloon Door Needs To Be Set | CARP | Yes
Aircon Not Draining | PLUM | Yes | Yes |  | Yes | Yes |  | Yes
Incomplete Wiring On Db | ELEC | Yes | Yes |  |  | Yes |  | Yes
Speakers Not Working | ELEC | Yes | [6 empty] | Yes |  |  | Yes
Shower Mixer Loose | PLUM |  | Yes | Yes | Yes | Yes |  | Yes
Swim Ladder Bolts Loose | DECK | [7 empty] | Yes
Ecu Not Labeled | ELEC | [8 empty] | Yes | Yes
Topup Engine Fluids | MECH | [8 empty] | Yes | Yes
Fuel Prefilter Pipe Clamps Loose | MECH | [8 empty] | Yes | Yes
Expansion Tank Pipe Clamps Loose | MECH | [8 empty] | Yes | Yes
Debree In Water Tank | PLUM |  | Yes | Yes |  | Yes
Toilet Seat Loose | PLUM |  | Yes | Yes | Yes | Yes |  | Yes
Water Tank Brace Loose | MECH |  | Yes | Yes |  | Yes
Toilet Roll Holder Loose | CARP |  | Yes | Yes | Yes | Yes |  | Yes
Shower Sump Not Working | ELEC |  | Yes | Yes | Yes | Yes |  | Yes
Morse Control Splitpins Not Properly Bent Open | MECH | [8 empty] | Yes | Yes
Loose L-Bracket On Starter Motor | MECH | [8 empty] | Yes | Yes
Steering Cable Loose | MECH | [8 empty] | Yes | Yes
Missing Labels At Filters Outboard | MECH | [8 empty] | Yes | Yes
Missing Label On Battery | MECH | [8 empty] | Yes | Yes
Shower Rose Leaking | PLUM |  | Yes | Yes | Yes | Yes |  | Yes
Shower Mixer Leaking | PLUM |  | Yes | Yes | Yes | Yes |  | Yes
Touch Light Not Working | ELEC | [6 empty] | Yes |  | Yes | Yes | Yes
Waste Tank Leaking | PLUM |  | Yes | Yes | Yes |  | Yes
Leak On Toilet Plumbing | PLUM |  | Yes | Yes | Yes | Yes |  | Yes
Davit Skew | DECK | [7 empty] | Yes
Fuel Tank Brace Loose | MECH |  | Yes |  |  | Yes
Fuel Clamps Loose At Bulkhead | MECH |  | Yes |  |  | Yes |  |  |  | Yes | Yes
Toilet Base Loose | PLUM |  | Yes | Yes | Yes | Yes |  | Yes
High Level Float Not Working | ELEC |  | Yes | Yes |  |  | Yes
Low Level Float Not Working | ELEC |  | Yes | Yes |  |  | Yes
Engine Fuse Not Covered | ELEC | [8 empty] | Yes | Yes
Morse Control Splitpins Not Properly Bent Open | MECH | [8 empty] | Yes | Yes
Battery Link Not Working | ELEC | [7 empty] | Yes | Yes | Yes
Aircon Pump Not Working | ELEC |  |  |  | Yes |  | Yes
Toilet Anti-Syphen Leaking | PLUM |  | Yes | Yes | Yes | Yes |  | Yes
Toilet Fresh Water Solenoid Not Working | ELEC |  | Yes | Yes | Yes | Yes |  | Yes
Touchlight In High Voltage Locker Not Working | ELEC | [5 empty] | Yes
Waste Tank Indicator Not Working | ELEC |  | Yes | Yes | Yes | Yes |  | Yes
Vhf Wire Not Pulled Through | ELEC | [7 empty] | Yes
Cabin Fan Not Working | ELEC |  | Yes | Yes | Yes | Yes |  | Yes
Waste Tank Indicator Light Not Fitted | ELEC |  | Yes | Yes | Yes | Yes |  | Yes
Missing Salt/Fresh Label At Toilet | PLUM |  | Yes | Yes | Yes | Yes |  | Yes
Shower Leaking Into Bilge | PLUM |  | Yes | Yes | Yes | Yes | Yes | Yes
Toilet Salt/Fresh Is Cross Wired | ELEC |  | Yes | Yes | Yes | Yes |  | Yes
Shower Head Leaking | PLUM |  | Yes | Yes | Yes | Yes |  | Yes
Toilet Flush Defective | PLUM |  | Yes | Yes | Yes | Yes |  | Yes
Incorrect Wiring On Finder Relay For Genset | ELEC | [6 empty] | Yes
Cabin Door Missing A Magnet Stopper | CARP |  | Yes | Yes | Yes | Yes |  | Yes
Leak On Water Heater | PLUM |  | Yes |  |  | Yes
Toilet Flush Is Cross Wired | ELEC |  | Yes | Yes | Yes | Yes |  | Yes
Aircon Pump Pipes Leaking | PLUM |  |  |  | Yes |  | Yes
Inverter Fans Not Working | ELEC | [5 empty] | Yes
Inverter Touch Light Not Working | ELEC | [5 empty] | Yes
Aircon Connection Box Not Labeled | ELEC |  |  |  | Yes |  | Yes
Aircon Box Incorrectly Wired | ELEC |  |  |  | Yes |  | Yes
Missing Timmer Module For Aircon Relays | ELEC |  |  |  | Yes |  | Yes
Hin Number Incorrect | FA | [7 empty] | Yes
Hin Number Sticker Not Fitted | FA | [7 empty] | Yes
Shore Power Label Not Fitted | FA | [7 empty] | Yes
R&C Decal Label / Dome Tag | FA | [7 empty] | Yes
Jammer Labels Not Fitted | DECK | [7 empty] | Yes |  |  | Yes
Raymic Fitting Upside Down | DECK | [7 empty] | Yes
Battery Cover Not Fitted | MECH | [6 empty] | Yes |  | Yes | Yes
Ecu Not Labeled | ELEC | [8 empty] | Yes | Yes
Loose Wire On Starter Solenoid | ELEC | [8 empty] | Yes | Yes
Galvanic Isolator Wires Loose | ELEC | [8 empty] | Yes
Steering Bar Laying On Raw Fibre Glass | MECH | [8 empty] | Yes | Yes
Alternator Negative Wire Not Connected | ELEC | [8 empty] | Yes | Yes
Morse Control Cables Are Badly Routed | MECH |  | Yes | [6 empty] | Yes | Yes
Shore Power Breakers Not Labeled And No Rail Stopper | ELEC | [8 empty] | Yes
Engine Harness Not Strapped Up | ELEC | [8 empty] | Yes | Yes
Engine Revs Do Not Align | MECH | [7 empty] | Yes | Yes | Yes
No Teak Steps To Coach Roof Fitted | CARP | [7 empty] | Yes
Pulleys And Rope Painter Needs To Be Installed | DECK | [10 empty] | Yes
Boom Labels Needs To Be Fitted | DECK | [10 empty] | Yes
Oven Gas Shutoff Label Not Fitted | PLUM | [10 empty] | Yes
Mfd Needs To Be Updated | ELEC | [7 empty] | Yes
Genset Breaker Not Labeled | ELEC | [10 empty] | Yes
Gas Solenoid Not Wired | ELEC | [10 empty] | Yes
Aircon Display Covers (Sf) | [12 empty] | Yes
All Fire Extinguishers To Be Installed (Sf) | [12 empty] | Yes

## Breakdown of areas
Saloon | Stbd Aft | Stbd Mid | Stbd Fwd | Prt Aft | Prt Passage | Prt Fwd | Aft Cockpit | Prt Engine Room | Stb Engine Room | FWD COCKPIT, SIDE DECKS AND COACH ROOF | Extras
Leak On Basin Plumbing | Leak On Basin Plumbing | Leak On Basin Plumbing | Leak On Basin Plumbing | Leak On Basin Plumbing | Junction Box Not Labeled | Leak On Basin Plumbing | Junction Box Not Labeled | Junction Box Not Labeled | Junction Box Not Labeled | Junction Box Not Labeled | Aircon Display Covers (Sf)
Basin Mixer Loose | Basin Mixer Loose | Basin Mixer Loose | Basin Mixer Loose | Basin Mixer Loose | Strip Lights Not Working | Basin Mixer Loose | Strip Lights Not Working | Ecu Not Labeled | Ecu Not Labeled | Strip Lights Not Working | All Fire Extinguishers To Be Installed (Sf)
Basin Cross Plumbed | Basin Cross Plumbed | Basin Cross Plumbed | Basin Cross Plumbed | Basin Cross Plumbed | Waste Tank Leaking | Basin Cross Plumbed | Mfd Not Showing Volts And Amps Of House Battery | Topup Engine Fluids | Topup Engine Fluids | Speakers Not Working
Junction Box Not Labeled | Junction Box Not Labeled | Junction Box Not Labeled | Junction Box Not Labeled | Junction Box Not Labeled | High Level Float Not Working | Junction Box Not Labeled | Autopilot Cross Wired | Fuel Prefilter Pipe Clamps Loose | Fuel Prefilter Pipe Clamps Loose | Touch Light Not Working
Strip Lights Not Working | Strip Lights Not Working | Strip Lights Not Working | Strip Lights Not Working | Strip Lights Not Working | Low Level Float Not Working | Strip Lights Not Working | Speakers Not Working | Expansion Tank Pipe Clamps Loose | Expansion Tank Pipe Clamps Loose | Jammer Labels Not Fitted
Inverter Not Programmed On Acdc | Aircon Switching On Wrong Pump | Shower Mixer Loose | Aircon Switching On Wrong Pump | Aircon Switching On Wrong Pump | Aircon Pump Not Working | Watermaker Not Wired | Swim Ladder Bolts Loose | Morse Control Splitpins Not Properly Bent Open | Morse Control Splitpins Not Properly Bent Open | Pulleys And Rope Painter Needs To Be Installed
Inverter Alarm Not Working | Aircon Not Working | Debree In Water Tank | Aircon Not Working | Aircon Not Working | Touchlight In High Voltage Locker Not Working | Aircon Switching On Wrong Pump | Davit Skew | Loose L-Bracket On Starter Motor | Loose L-Bracket On Starter Motor | Boom Labels Needs To Be Fitted
Watermaker Not Wired | Aircon Not Draining | Toilet Seat Loose | Aircon Not Draining | Aircon Not Draining | Shower Leaking Into Bilge | Aircon Not Working | Battery Link Not Working | Steering Cable Loose | Steering Cable Loose | Oven Gas Shutoff Label Not Fitted
Loose Wires Behind Acdc | Incomplete Wiring On Db | Water Tank Brace Loose | Shower Mixer Loose | Incomplete Wiring On Db | Aircon Pump Pipes Leaking | Aircon Not Draining | Vhf Wire Not Pulled Through | Missing Labels At Filters Outboard | Missing Labels At Filters Outboard | Genset Breaker Not Labeled
Bilge Override Lights Not Working | Shower Mixer Loose | Toilet Roll Holder Loose | Toilet Seat Loose | Shower Mixer Loose | Inverter Fans Not Working | Incomplete Wiring On Db | Hin Number Incorrect | Missing Label On Battery | Missing Label On Battery | Gas Solenoid Not Wired
Filter Tap Fitted Wrong (Too Tight) | Debree In Water Tank | Shower Sump Not Working | Toilet Roll Holder Loose | Debree In Water Tank | Inverter Touch Light Not Working | Shower Mixer Loose | Hin Number Sticker Not Fitted | Touch Light Not Working | Touch Light Not Working
Galley Fridge Not Working | Toilet Seat Loose | Shower Rose Leaking | Shower Sump Not Working | Toilet Seat Loose | Aircon Connection Box Not Labeled | Toilet Seat Loose | Shore Power Label Not Fitted | Fuel Clamps Loose At Bulkhead | Fuel Clamps Loose At Bulkhead
Genset Isolator Switch Not Mounted | Water Tank Brace Loose | Shower Mixer Leaking | Shower Rose Leaking | Water Tank Brace Loose | Aircon Box Incorrectly Wired | Toilet Roll Holder Loose | R&C Decal Label / Dome Tag | Engine Fuse Not Covered | Engine Fuse Not Covered
2X Amplifiers Not Fitted | Toilet Roll Holder Loose | Waste Tank Leaking | Shower Mixer Leaking | Toilet Roll Holder Loose | Missing Timmer Module For Aircon Relays | Shower Sump Not Working | Jammer Labels Not Fitted | Morse Control Splitpins Not Properly Bent Open | Morse Control Splitpins Not Properly Bent Open
Saloon Clear Plastic Db Cover Not Mounted | Shower Sump Not Working | Leak On Toilet Plumbing | Waste Tank Leaking | Shower Sump Not Working |  | Shower Rose Leaking | Raymic Fitting Upside Down | Battery Link Not Working | Battery Link Not Working
Table Top Not Installed | Shower Rose Leaking | Toilet Base Loose | Leak On Toilet Plumbing | Shower Rose Leaking |  | Shower Mixer Leaking | Engine Revs Do Not Align | Battery Cover Not Fitted | Battery Cover Not Fitted
Fire Blanket Not Fitted (Sf) | Shower Mixer Leaking | High Level Float Not Working | Toilet Base Loose | Shower Mixer Leaking |  | Touch Light Not Working | No Teak Steps To Coach Roof Fitted | Ecu Not Labeled | Ecu Not Labeled
House Batteries Not Booted | Waste Tank Leaking | Low Level Float Not Working | Aircon Pump Not Working | Leak On Toilet Plumbing |  | Leak On Toilet Plumbing | Mfd Needs To Be Updated | Loose Wire On Starter Solenoid | Loose Wire On Starter Solenoid
Mfd Not Showing Volts And Amps Of House Battery | Leak On Toilet Plumbing | Toilet Anti-Syphen Leaking | Toilet Anti-Syphen Leaking | Fuel Tank Brace Loose |  | Toilet Base Loose |  | Galvanic Isolator Wires Loose | Steering Bar Laying On Raw Fibre Glass
Co2 Sensor Not Mounted | Fuel Tank Brace Loose | Toilet Fresh Water Solenoid Not Working | Toilet Fresh Water Solenoid Not Working | Fuel Clamps Loose At Bulkhead |  | Toilet Anti-Syphen Leaking |  | Steering Bar Laying On Raw Fibre Glass | Alternator Negative Wire Not Connected
Autopilot Cross Wired | Fuel Clamps Loose At Bulkhead | Waste Tank Indicator Not Working | Waste Tank Indicator Not Working | Toilet Base Loose |  | Toilet Fresh Water Solenoid Not Working |  | Alternator Negative Wire Not Connected | Morse Control Cables Are Badly Routed
Galley Fridge Compressor Loosely Mounted | Toilet Base Loose | Cabin Fan Not Working | Cabin Fan Not Working | Toilet Anti-Syphen Leaking |  | Waste Tank Indicator Not Working |  | Morse Control Cables Are Badly Routed | Engine Harness Not Strapped Up
Saloon Tap Weight Mounted On Wrong Side Of Hose | High Level Float Not Working | Waste Tank Indicator Light Not Fitted | Waste Tank Indicator Light Not Fitted | Toilet Fresh Water Solenoid Not Working |  | Cabin Fan Not Working |  | Shore Power Breakers Not Labeled And No Rail Stopper | Engine Revs Do Not Align
Telly Mute Not Working | Low Level Float Not Working | Missing Salt/Fresh Label At Toilet | Missing Salt/Fresh Label At Toilet | Waste Tank Indicator Not Working |  | Waste Tank Indicator Light Not Fitted |  | Engine Harness Not Strapped Up
Nmma Label Needs To Be Mounted | Toilet Anti-Syphen Leaking | Shower Leaking Into Bilge | Shower Leaking Into Bilge | Cabin Fan Not Working |  | Missing Salt/Fresh Label At Toilet |  | Engine Revs Do Not Align
Inverter Alarm Not Working | Toilet Fresh Water Solenoid Not Working | Toilet Salt/Fresh Is Cross Wired | Toilet Salt/Fresh Is Cross Wired | Waste Tank Indicator Light Not Fitted |  | Shower Leaking Into Bilge
Aircon Switching On Wrong Pump | Waste Tank Indicator Not Working | Shower Head Leaking | Shower Head Leaking | Missing Salt/Fresh Label At Toilet |  | Toilet Salt/Fresh Is Cross Wired
Incomplete Wiring Behind Acdc Panel | Cabin Fan Not Working | Toilet Flush Defective | Toilet Flush Defective | Shower Leaking Into Bilge |  | Shower Head Leaking
Incomplete Wiring At Main Saloon Db | Waste Tank Indicator Light Not Fitted | Cabin Door Missing A Magnet Stopper | Cabin Door Missing A Magnet Stopper | Toilet Salt/Fresh Is Cross Wired |  | Toilet Flush Defective
Aircon Not Working | Missing Salt/Fresh Label At Toilet | Toilet Flush Is Cross Wired | Toilet Flush Is Cross Wired | Shower Head Leaking |  | Incorrect Wiring On Finder Relay For Genset
Saloon Door Needs To Be Set | Shower Leaking Into Bilge |  | Aircon Pump Pipes Leaking | Toilet Flush Defective |  | Cabin Door Missing A Magnet Stopper
Aircon Not Draining | Toilet Salt/Fresh Is Cross Wired |  | Aircon Connection Box Not Labeled | Cabin Door Missing A Magnet Stopper |  | Toilet Flush Is Cross Wired
Incomplete Wiring On Db | Shower Head Leaking |  | Aircon Box Incorrectly Wired | Leak On Water Heater |  | Battery Cover Not Fitted
Speakers Not Working | Toilet Flush Defective |  | Missing Timmer Module For Aircon Relays | Toilet Flush Is Cross Wired
Cabin Door Missing A Magnet Stopper
Leak On Water Heater
Toilet Flush Is Cross Wired
Morse Control Cables Are Badly Routed